## Screens & Dialogs
ID | Actor (User Role) | Module | Name | Type | Difficulty | Member | Status | Route / Component
S01 | All Staff | Auth | Login | Screen | Easy | M5 - Platform & Admin | Live | /login
S02 | All Staff | Auth | Forgot / Reset Password | Screen | Easy | M5 - Platform & Admin | Live | /forgot-password
S03 | All Staff | Profile | Account Settings | Screen | Easy | M5 - Platform & Admin | Live | /profile
D01 | All Staff | Profile | Change Password Dialog | Dialog | Easy | M5 - Platform & Admin | Live | ChangePasswordDialog
D02 | All Staff | Profile | Two-Factor Setup Dialog | Dialog | Medium | M5 - Platform & Admin | Live | TwoFactorSetupDialog
S04 | All Staff | Reports | Overview Dashboard | Screen | Medium | M4 - Ads & Analytics | Live | / (AnalyticsReportsPage)
S05 | All Staff | Notifications | Notification Center | Screen | Easy | M5 - Platform & Admin | Live | /notifications
S06 | Admin / Director | Admin & RBAC | Admin Console - Users tab | Screen | Medium | M5 - Platform & Admin | Live | /system
D03 | Admin / Director | Admin & RBAC | User Create/Edit Dialog | Dialog | Easy | M5 - Platform & Admin | Live | AdminUserModal
S07 | Admin / Director | Admin & RBAC | Admin Console - Roles & Permissions tab | Screen | Medium | M5 - Platform & Admin | Live | /system
D04 | Admin / Director | Admin & RBAC | Role Create/Edit Dialog | Dialog | Medium | M5 - Platform & Admin | Live | AdminRoleModal
S08 | Admin / Director | Admin & RBAC | Admin Console - Integrations tab (API keys & channel credentials) | Screen | Medium | M5 - Platform & Admin | Live | /system
D05 | Admin / Director | Admin & RBAC | API Key Create Dialog | Dialog | Easy | M5 - Platform & Admin | Live | AdminKeyModal
D06 | Admin / Director | Channels | Pancake Channel Connection Dialog | Dialog | Hard | M1 - Omnichannel Inbox & Chat | Live | AdminPancakeChannelModal
S09 | Admin / Director | Admin & RBAC | Admin Console - Scheduled Jobs tab | Screen | Medium | M5 - Platform & Admin | Live | /system
D07 | Admin / Director | Admin & RBAC | Schedule Run Detail Dialog | Dialog | Easy | M5 - Platform & Admin | Live | AdminScheduleRunDialog
D08 | Admin / Director | Admin & RBAC | Recurring Execution Detail Dialog | Dialog | Easy | M5 - Platform & Admin | Live | AdminRecurringExecutionDialog
S10 | Admin / Director | Admin & RBAC | Admin Console - System Errors tab | Screen | Medium | M5 - Platform & Admin | Live | /system
D09 | Admin / Director | Admin & RBAC | System Error Detail Drawer | Dialog | Easy | M5 - Platform & Admin | Live | AdminSystemLogsTab
S11 | Admin / Director | Admin & RBAC | Admin Console - Audit Log tab | Screen | Medium | M5 - Platform & Admin | Live | /system
D10 | Admin / Director | Admin & RBAC | Audit Entry Detail Dialog | Dialog | Easy | M5 - Platform & Admin | Live | AdminAuditTab
S12 | Admin / Director | Channels | Channel Management | Screen | Medium | M1 - Omnichannel Inbox & Chat | Live | /system/channels
D11 | Admin / Director | Channels | Channel Create/Edit Dialog | Dialog | Medium | M1 - Omnichannel Inbox & Chat | Live | ChannelManagementPage (inline)
S13 | QA & Prompt Engineer | LLM Providers | LLM Model Configuration | Screen | Medium | M5 - Platform & Admin | Live | /llm-providers
D12 | QA & Prompt Engineer | LLM Providers | Provider Create/Edit Dialog | Dialog | Medium | M5 - Platform & Admin | Live | LlmProvidersPage (inline)
D13 | QA & Prompt Engineer | LLM Providers | API Key Rotate Dialog | Dialog | Easy | M5 - Platform & Admin | Live | LlmProvidersPage (inline)
D14 | QA & Prompt Engineer | LLM Providers | Embedding Config Create/Edit Dialog | Dialog | Medium | M5 - Platform & Admin | Live | LlmProvidersPage (inline)
D15 | QA & Prompt Engineer | LLM Providers | Embedding Key Rotate Dialog | Dialog | Easy | M5 - Platform & Admin | Live | LlmProvidersPage (inline)
S14 | QA & Prompt Engineer | Prompts & Skills | Agent Instruction Configuration | Screen | Hard | M5 - Platform & Admin | Live | /prompts
D16 | QA & Prompt Engineer | Prompts & Skills | Edit Instruction Dialog | Dialog | Medium | M5 - Platform & Admin | Live | PromptConfigurationPage (inline)
D17 | QA & Prompt Engineer | Prompts & Skills | Prompt Sandbox Test Dialog | Dialog | Medium | M5 - Platform & Admin | Live | SandboxModal
S15 | QA & Prompt Engineer | Agents | Agent Dashboard (Monitoring & Config) | Screen | Hard | M5 - Platform & Admin | Live | /agents
D18 | QA & Prompt Engineer | Agents | Create Sub-Agent Dialog | Dialog | Hard | M5 - Platform & Admin | Live | CreateSubAgentDialog
D19 | QA & Prompt Engineer | Agents | Plan Suggestions Dialog | Dialog | Medium | M5 - Platform & Admin | Live | PlanSuggestionsDialog
D20 | QA & Prompt Engineer | Agents | Run Compare Dialog | Dialog | Medium | M5 - Platform & Admin | Live | RunCompareDialog
D21 | QA & Prompt Engineer | Agents | Task Intervention Dialog | Dialog | Hard | M5 - Platform & Admin | Live | TaskInterventionDialog
D22 | QA & Prompt Engineer | Agents | Approval Policy Dialog | Dialog | Medium | M5 - Platform & Admin | Live | AgentDashboardPage (inline)
D23 | QA & Prompt Engineer | Agents | Plan JSON Editor / System Prompt Viewer Dialog | Dialog | Hard | M5 - Platform & Admin | Live | OrchestrationPanel (inline)
D24 | QA & Prompt Engineer | Agents | Create Schedule Dialog | Dialog | Medium | M5 - Platform & Admin | Live | SchedulesCard (inline)
D25 | QA & Prompt Engineer | Agents | Task DAG Edge Data Dialog | Dialog | Medium | M5 - Platform & Admin | Live | TaskDagCanvas (inline)
S16 | QA & Prompt Engineer | Agents | Orchestration Sessions | Screen | Hard | M5 - Platform & Admin | Live | /agents/runs
S17 | QA & Prompt Engineer | Agents | Session Detail (Trace) | Screen | Hard | M5 - Platform & Admin | Live | /agents/runs/:sessionId
S18 | QA & Prompt Engineer | Agents | Agents Office (pixel-art visualization) | Screen | Medium | M5 - Platform & Admin | Live | /agents-office
S19 | Admin / Director | Ops | Task Logs | Screen | Medium | M5 - Platform & Admin | Live | /logs
S20 | PM / Data Analyst | Ops | AI Cost Management (Token Usage) | Screen | Medium | M5 - Platform & Admin | Live | /tokens
D26 | All Staff | Ops | Job Center Dialog (cross-cutting) | Dialog | Easy | M5 - Platform & Admin | Live | JobCenterDialog
S21 | Sales Rep (Sale) | Inbox | Multichannel Inbox (Conversations) | Screen | Hard | M1 - Omnichannel Inbox & Chat | Live | /conversations
D27 | Sales Rep (Sale) | Inbox | Customer Info Drawer (mobile) | Dialog | Easy | M1 - Omnichannel Inbox & Chat | Live | ConversationsPage (inline)
D28 | Sales Rep (Sale) | Inbox | Quick Reply Create/Edit Dialog | Dialog | Easy | M2 - Sale Assist & Lead CRM | Live | SaleAssistPanel (inline)
S22 | Sales Rep (Sale) | Inbox | Agent Hub (unified live workspace) | Screen | Hard | M1 - Omnichannel Inbox & Chat | Live | /agent-hub, /inbox/:channelId
D29 | Sales Rep (Sale) | Inbox | Command Palette | Dialog | Medium | M1 - Omnichannel Inbox & Chat | Live | CommandPalette
D30 | Sales Rep (Sale) | Inbox | Daily Summary Popup | Dialog | Easy | M1 - Omnichannel Inbox & Chat | Live | DailySummaryPopup
S23 | QA & Prompt Engineer | Knowledge Base | Knowledge Base | Screen | Medium | M1 - Omnichannel Inbox & Chat | Live | /kb
D31 | QA & Prompt Engineer | Knowledge Base | KB Module Create/Edit Dialog | Dialog | Medium | M1 - Omnichannel Inbox & Chat | Live | ModuleFormModal
D32 | QA & Prompt Engineer | Knowledge Base | KB Q&A Test Case Dialog | Dialog | Medium | M1 - Omnichannel Inbox & Chat | Live | QaModal
D33 | QA & Prompt Engineer | Knowledge Base | KB Auto-Classify Dialog | Dialog | Medium | M1 - Omnichannel Inbox & Chat | Live | KbAutoClassifyModal
D34 | QA & Prompt Engineer | Knowledge Base | Archive Module Confirm Dialog | Dialog | Easy | M1 - Omnichannel Inbox & Chat | Live | KnowledgeBasePage (inline)
D35 | QA & Prompt Engineer | Knowledge Base | Reject KB Suggestion Dialog | Dialog | Easy | M1 - Omnichannel Inbox & Chat | Live | KbSuggestionsPanel (inline)
S24 | Sales Rep (Sale) | Leads | Leads (List + Kanban Pipeline + Detail) | Screen | Hard | M2 - Sale Assist & Lead CRM | Live | /leads
D36 | Sales Rep (Sale) | Leads | Lead Detail Drawer (Timeline / Context) | Dialog | Medium | M2 - Sale Assist & Lead CRM | Live | LeadDrawer
S25 | Growth Strategist (MKT Lead) | Content | Content Workspace - Review Queue tab | Screen | Medium | M3 - Content & Document | Live | /content
S26 | Growth Strategist (MKT Lead) | Content | Content Workspace - Content Calendar tab | Screen | Medium | M3 - Content & Document | Live | /content
D37 | Growth Strategist (MKT Lead) | Content | Trend Settings Dialog | Dialog | Medium | M3 - Content & Document | Live | TrendSettingsDialog
D38 | Growth Strategist (MKT Lead) | Content | Weekly Trend Ideas Dialog | Dialog | Easy | M3 - Content & Document | Live | ContentWorkspacePage (inline)
D39 | Growth Strategist (MKT Lead) | Content | Schedule Publish Dialog | Dialog | Easy | M3 - Content & Document | Live | ContentWorkspacePage (inline)
D40 | Growth Strategist (MKT Lead) | Content | Override Approve Dialog | Dialog | Medium | M3 - Content & Document | Live | ContentWorkspacePage (inline)
D41 | Growth Strategist (MKT Lead) | Content | Reject Publish Dialog | Dialog | Easy | M3 - Content & Document | Live | ContentWorkspacePage (inline)
S27 | Sales Rep (Sale) | Documents | Document Library & Quote Generator | Screen | Medium | M3 - Content & Document | Live | /documents
S28 | PM / Data Analyst | Reports | Report Detail (Drill-down) | Screen | Medium | M4 - Ads & Analytics | Live | /reports/:reportId
D42 | PM / Data Analyst | Reports | Export Report Dialog | Dialog | Easy | M4 - Ads & Analytics | Live | AnalyticsReportsPage (inline)
S29 | End Customer (public) | Public Widget | Chat Widget (embeddable) | Screen | Hard | M1 - Omnichannel Inbox & Chat | Live | /chat-widget
S30 | End Customer (public) | Public Widget | Support FAQ (tenant-branded) | Screen | Medium | M1 - Omnichannel Inbox & Chat | Live | /support
DRIFT |  |  | Planned in the old doc or backed by an API, but with NO current frontend screen
NB01 | Growth Strategist (MKT Lead) | Content | Competitor Tracking | Screen | Medium | M4 - Ads & Analytics | Backend only | CompetitorsEndpoints, no frontend route
NB02 | PM / Data Analyst | Content | A/B Experiments | Screen | Medium | M4 - Ads & Analytics | Backend only | ExperimentsEndpoints, no frontend route
NB03 | Sales Rep (Sale) | Inbox | Chat Scenario Authoring (50 scripted scenarios) | Screen | Medium | M1 - Omnichannel Inbox & Chat | Backend only | ChatScenariosEndpoints, no frontend route
NB04 | Sales Lead (Sales Manager) | Leads | Lead Scoring Rule Configuration | Screen | Medium | M2 - Sale Assist & Lead CRM | Not built | no scoring-rule screen or component found
NB05 | Sales Lead (Sales Manager) | Leads | Drip Sequence Configuration | Screen | Medium | M2 - Sale Assist & Lead CRM | Not built | no drip-sequence screen or component found
NB06 | Growth Strategist (MKT Lead) | Ads | Ads Campaign Management | Screen | Hard | M4 - Ads & Analytics | Removed | Ads module decommissioned 2026-08-09; DB tables retained
NB07 | Growth Strategist (MKT Lead) | Ads | Ads Rule Configuration | Screen | Medium | M4 - Ads & Analytics | Removed | Ads module decommissioned 2026-08-09
NB08 | Growth Strategist (MKT Lead) | Ads | Ads Campaign Detail + Action Log | Screen | Medium | M4 - Ads & Analytics | Removed | Ads module decommissioned 2026-08-09

## Non-Functional Reqs (NFR)
ID | Type | Requirement | Description / Criteria | Difficulty | Person-Days
N01 | Performance | Response latency | p95 first-token < 2s, full reply < 8s; streamed. | Hard | 3
N02 | Performance | Throughput | A few hundred concurrent sessions; heavy work goes through a queue. | Medium | 3
N03 | Performance | LLM context caching | Reduces cost and latency for RAG calls that repeat context. | Medium | 2
N04 | Reliability | External-call fault tolerance | Polly retry / timeout / circuit breaker. | Medium | 3
N05 | Reliability | Graceful degradation | One failing agent does not take down the system; falls back to a human. | Hard | 3
N06 | Reliability | Health check + auto-restart | Recovery under 10s. | Easy | 1.5
N07 | Reliability | Queue & retry | RabbitMQ offloads heavy work, with retry and an optional DLQ. | Medium | 3
N08 | Security | Authentication & authorization | JWT + RBAC scoped by role and module. | Medium | 3
N09 | Security | Secret management | API keys are encrypted at rest and never exposed to the client. | Medium | 2
N10 | Security | Webhook authentication | Verifies the Pancake webhook signature. | Medium | 1.5
N11 | Security | Audit log | Records every administrative action. | Easy | 2
N12 | Data | Backup & restore | Daily database backup; source files kept durable. | Medium | 2
N13 | Data | Data privacy | Handles customer data with per-tenant isolation. | Medium | 3
N14 | Scalability | Stateless / horizontal-ready | State lives in Redis/DB, enabling horizontal scale. | Hard | 3
N15 | Operations | Centralized logging | Serilog; traced per request/session. | Easy | 2
N16 | Operations | Monitoring & alerting | Metrics plus alerts for errors and queue backlog. | Medium | 3
N17 | Usability | Localization / UX | Responsive UI with clear error messages. | Medium | 2.5
N18 | Compatibility | Channel adapter | Adding or swapping a channel does not require touching the core. | Hard | 3
TOTAL

## Docs-Test-Management
ID | Type | Item | Description | Difficulty | Person-Days
O01 | Documentation | Requirements specification (SRS) | FR + NFR, use cases. | Medium | 4
O02 | Documentation | Design document (SDD) | Architecture, diagrams, DB schema, API spec. | Medium | 4
O03 | Documentation | User manual | For end users. | Easy | 2
O04 | Documentation | Deployment / operations runbook | Setup, deployment, runbook. | Easy | 2
O05 | Testing | Unit tests | Core: orchestrator, adapters, RAG. | Medium | 6
O06 | Testing | Integration tests | End-to-end flows. | Medium | 5
O07 | Testing | API tests | REST API test suite. | Medium | 3
O08 | Testing | Light load testing | Verifies the throughput/latency NFRs. | Medium | 3
O09 | Testing | UAT & bug-fix cycle | Acceptance testing plus a bug-fix cycle. | Medium | 5
O10 | Management | UI/UX design | Wireframe to mockup for every screen and dialog. | Hard | 9
O11 | Management | Project management & meetings | Coordination, review, reporting. | Medium | 6
TOTAL

## Summary
SUMMARY - ClawBot (rebuilt from current code)
Category | Count | Person-Days
Screens + Dialogs (live) | 72
Non-Functional Requirements (NFR) | 18
Docs / Test / Management | 11
TOTAL | 101
UI breakdown
Screens (full page) | 30
Dialogs / modals | 42
Planned / backend-only / removed (drift) | 8
Breakdown by member
M1 - Omnichannel Inbox & Chat | 6 screens + 10 dialogs = 16 items
M2 - Sale Assist & Lead CRM | 1 screens + 2 dialogs = 3 items
M3 - Content & Document | 3 screens + 5 dialogs = 8 items
M4 - Ads & Analytics | 2 screens + 1 dialogs = 3 items
M5 - Platform & Admin | 18 screens + 24 dialogs = 42 items
This sheet was rebuilt against the actual frontend routes (src/frontend/clawbot-web/src/app/routes.tsx) and
backend endpoints (src/api/Clawbot.Api/Endpoints) as of the current branch.
Added (existed in code but were missing from the old sheet): Document Library & Quote Generator, Admin & RBAC
console (6 tabs), Channel Management, Notification Center, Agent Hub, Agents Office, Task Logs, AI Cost
Management, Prompts/Skills configuration, Public Widget + Support FAQ, LLM Provider & Embedding Config screens.
Flagged as backend-only (API exists, no frontend screen): Competitor Tracking, A/B Experiments,
Chat Scenario Authoring.
Flagged as not built: Lead Scoring Rule Configuration, Drip Sequence Configuration.
Flagged as removed: Ads Campaign Management, Ads Rule Configuration, Ads Campaign Detail (module
decommissioned 2026-08-09; database tables were kept, the UI and endpoints were not).
COLOR LEGEND - MEMBER
M1 - Omnichannel Inbox & Chat
M2 - Sale Assist & Lead CRM
M3 - Content & Document
M4 - Ads & Analytics
M5 - Platform & Admin
All (shared)