## Security
Test Case ID | Scenario Name | Role / Session | Given | When | Then (Expected) | Priority | Status | Defect ID | Notes
TC-SEC-001 | Tenant isolation on every data query | Tenant B admin | Two active tenants A and B, each with its own conversations, leads and knowledge modules | Sign in as the tenant B admin and request a record that belongs to tenant A by its identifier | HTTP 404 is returned and no tenant A payload appears in the response body | Critical | Pass |  | Executed 2026-08-18. Checked on conversations, leads and knowledge modules; every attempt returned 404 with an empty body.
TC-SEC-002 | Permission fence on a protected endpoint | Sale role | A sale user whose role is not granted the agent.manage permission | Call the agent skill write endpoint with a valid access token | HTTP 403 is returned, the skill store is unchanged and the attempt is written to the audit log | Critical | Pass |  | Executed 2026-08-18. Retested after the permission code on the skill endpoints was corrected; the store was unchanged and the audit row was present.
TC-SEC-003 | Lead visibility is scoped to the assigned inbox | Sale role | A sale user who owns inbox 1 only, while leads exist on inbox 1 and inbox 2 | Open the lead list page and inspect the returned identifiers | Only leads attached to inbox 1 are returned; the read all permission is required to see the rest | High | Pass |  | Executed 2026-08-18. A sale user saw 7 of 19 leads; the manager account with the read all permission saw all 19.
TC-SEC-004 | Access token expiry and refresh rotation | Any authenticated user | A signed in session holding one access token and one refresh token | Wait for the access token lifetime to elapse, then call a protected endpoint and refresh once | The expired token is rejected with HTTP 401; refresh returns a new pair and the previous refresh token is revoked | Critical | Pass |  | Executed 2026-08-18. Replaying the rotated refresh token outside the grace window was rejected as expected.
TC-SEC-005 | Brute force protection on the sign in endpoint | Anonymous | A valid account and a rate limit of thirty sign in attempts per minute per address | Submit repeated sign in attempts with a wrong password beyond the configured limit | Further attempts return HTTP 429 and the account is not disclosed as existing or missing | High | Pass |  | Executed 2026-08-18. The 31st attempt returned 429; the response was identical for a known and an unknown address.
TC-SEC-006 | Provider credentials are stored encrypted | Tenant admin | A language model provider key and a channel token saved through the settings page | Read the social credentials and llm configuration rows straight from the database | Stored values are ciphertext; no plain key is readable and the user interface only shows a masked value | Critical | Pass |  | Executed 2026-08-18. Both rows held ciphertext and the settings page showed only the last four characters.
TC-SEC-007 | Server side request forgery guard on a provider base address | Tenant admin | The language model configuration form accepts a custom base address | Save a configuration pointing at an internal host such as the loopback interface or a private range | The value is rejected with a validation error and no outbound request is issued | Critical | Pass |  | Executed 2026-08-19. A public name resolving to a private address was also rejected, so the guard resolves the host before deciding.
TC-SEC-008 | Personal data is redacted in derived text | Tenant admin | A customer conversation containing a phone number, an email address and an address | Trigger a summary and inspect the stored summary, the agent trace and the system log rows | Derived text keeps the meaning but the personal fields are masked; only the raw message keeps them | High | Pass |  | Executed 2026-08-19. The phone number, the email address and the street address were masked in all three stores.
TC-SEC-009 | Webhook payloads are authenticated before processing | Anonymous | The channel webhook endpoint is published and reachable | Post a forged payload without a valid signature, then post the same payload with a valid signature | The forged payload is rejected without side effects; only the signed payload creates a message row | Critical | Pass |  | Executed 2026-08-19. Verified on the native channel webhook and on the polling bridge entry point.
TC-SEC-010 | Uploaded documents are only reachable through an authorised endpoint | Tenant B user | A knowledge document uploaded by tenant A and stored in object storage | Request the storage path directly with a tenant B session and with no session at all | Both attempts return HTTP 403 or 404 and the file content is never streamed | Critical | Pass |  | Executed 2026-08-19. No response payload exposed a direct storage address.
TC-SEC-011 | Error responses do not leak internals | Any authenticated user | An endpoint that fails because a downstream dependency is unavailable | Force the dependency down and call the endpoint, then read the response body | The client receives a generic problem response; the stack trace and connection string stay in the server log | Medium | Fail | DEF-201 | Executed 2026-08-19. With the cache down, one endpoint returned the exception detail in the response body. The database and message queue outages behaved correctly. Fix scheduled for the next release.
TC-SEC-012 | Spend guard stops a runaway agent session | Tenant admin | A tenant whose accumulated model spend is at the configured ceiling | Start a new agent session that would call a paid model | The session is refused with an explicit budget message and no paid call is issued | High | Blocked |  | Not executed in this round: driving a real account up to the ceiling needs a paid provider budget that was not available. Covered indirectly by the cost tracker unit tests.
TC-SEC-013 | Transport is encrypted end to end | (N/A) | A staging deployment published behind the public domain | Walk one complete business flow through the browser and inspect every request | Every request uses transport layer security, no mixed content warning appears and strict transport security is present | Medium | Pass |  | Executed 2026-08-20. The websocket upgrade used by the notification and inbox hubs was also encrypted.
TC-SEC-014 | Audit trail for privileged changes | Tenant admin | An administrator account with user management permission | Create one user, revoke one role and deactivate one account | Each action writes an audit row with actor, target, action and timestamp that survives a service restart | High | Pass |  | Executed 2026-08-20. All three rows were still present after the service was restarted.
TC-SEC-015 | Cross-tenant object access is denied via direct identifier | Tenant B admin | A document owned by tenant A whose identifier is known | GET /api/documents/{tenantAId} as tenant B | HTTP 404 and no document payload is returned | Critical | Pass |  | Executed 2026-08-19. Tested on documents, briefs and content items; every attempt returned 404.
TC-SEC-016 | Role update takes effect without re-login | Tenant admin | A sale user currently signed in | Grant an additional permission to the user role and retry the endpoint | User gains the permission on the next request without signing out | High | Pass |  | Executed 2026-08-20. Permission was applied on the next request after the role update.
TC-SEC-017 | Expired refresh token is rejected | Anonymous | A refresh token whose expiry is in the past | POST /auth/refresh with the expired token | HTTP 401 and no new token pair is issued | High | Pass |  | Executed 2026-08-18. Token created one hour before expiry returned 401 as expected.
TC-SEC-018 | Tenant header cannot be spoofed | Anonymous | A valid tenant B session | Send a request with X-Tenant-Id set to tenant A | Tenant from the session is used; identifier from the header is ignored or rejected | Critical | Pass |  | Executed 2026-08-19. Forged header had no effect on data visibility.
TC-SEC-019 | Rate limit is per tenant and per address | Anonymous | Two tenants sharing the same address | Exhaust the sign in limit for tenant A then try tenant B | Tenant B is not blocked by tenant A limit | Medium | Pass |  | Executed 2026-08-18. Tenant B still returned 200 after tenant A hit 429.
TC-SEC-020 | Session revocation invalidates all refresh tokens | Tenant admin | A user with two active sessions | Revoke all sessions for the user then try either refresh token | Both refresh tokens return HTTP 401 | Critical | Pass |  | Executed 2026-08-20. Both tokens were rejected after revocation.
TC-SEC-021 | Data export requires an explicit permission | Sale role | A sale user without the export permission | Call GET /api/inbox/conversations/{id}/export.csv | HTTP 403 and no file is streamed | Medium | Pass |  | Executed 2026-08-20. The same call succeeded once the export permission was granted.
TC-SEC-022 | Backup snapshots are encrypted at rest | Tenant admin | A nightly database backup file on the storage volume | Inspect the backup file directly on disk without the decryption key | The file content is not readable as plain SQL or plain text | High | Pass |  | Executed 2026-08-20. The backup volume uses provider-side encryption at rest; the raw file was opaque.
TC-SEC-023 | Security response headers are present on every page | Anonymous | The staging deployment behind the public domain | Fetch the main page and an API response and inspect the response headers | Content-Security-Policy, X-Content-Type-Options and X-Frame-Options are present | Medium | Pass |  | Executed 2026-08-20. All three headers were present on both the page and the API response.
TC-SEC-024 | Uploaded document rejects an executable extension | Content editor | The knowledge base document upload endpoint | Upload a file renamed to end in .exe | The upload is rejected with a validation error before it reaches storage | High | Pass |  | Executed 2026-08-20. The rejection happened on content-type sniffing, not just the file extension.
TC-SEC-025 | A read-only API key cannot reach a write endpoint by path variation | Anonymous | An API key issued with scope=read | Call a write endpoint using an alternate casing and trailing slash | HTTP 403 regardless of the path variation used | Medium | Pass |  | Executed 2026-08-20. Three path variations were tried; all were rejected consistently.
TC-SEC-026 | Concurrent scheduled jobs across tenants do not cross-contaminate data | Tenant admin | Two tenants each with a due scheduled job at the same minute | Let both schedules fire at the same time and inspect the results written by each | Each job only reads and writes its own tenant's rows | Critical | Pass |  | Executed 2026-08-20. Ran both jobs concurrently five times; no cross-tenant row was ever written.

## Performance
Test Case ID | Scenario | Tool | Target | Actual | Status | Defect IDs | Notes
TC-PERF-001 | Agent dashboard first load with a single user | Manual (browser developer tools) | Under two seconds to interactive | 1.4 s | Pass |  | Measured 2026-08-19 on the staging build with a warm cache, median of five loads.
TC-PERF-002 | Inbox conversation list with ten thousand stored messages | Manual (browser developer tools) | Under one second for the first page of twenty items | 0.6 s | Pass |  | Measured 2026-08-19. The endpoint is paginated; no unbounded query was observed in the server log.
TC-PERF-003 | Automatic reply latency from inbound message to outbound reply | Manual timing against service logs | Under eight seconds at the median for a short question | 9.4 s | Fail | DEF-202 | Measured 2026-08-19 over twenty exchanges. Provider latency accounted for about seven seconds of the total, so the target needs either a faster model or a revised figure.
TC-PERF-004 | Knowledge retrieval for one question | Manual timing against service logs | Under two seconds for the retrieval step alone | 1.1 s | Pass |  | Measured 2026-08-19 on the language model retrieval path that is active by default.
TC-PERF-005 | Content draft generation completes as a background job | Manual (job centre dialog) | Under ninety seconds for one article draft | 62 s | Pass |  | Measured 2026-08-20. The user interface stayed responsive for the whole run.
TC-PERF-006 | Concurrent load on the read heavy endpoints | k6 when available, otherwise manual | Fifty concurrent users with an error rate under one percent |  | Not Run |  | Deferred to the next release: no load generation environment was available for this round. Recorded in the out of scope section of the test plan.
TC-PERF-007 | Document upload and indexing of a five megabyte file | Manual (browser developer tools) | Upload under ten seconds, indexing under two minutes | Upload 4 s, indexing 71 s | Pass |  | Measured 2026-08-20. Indexing ran in the background and reported progress through the job centre.
TC-PERF-008 | Scheduled agent batch does not block interactive traffic | Manual observation | Dashboard response time stays under three seconds while the batch runs | 2.2 s | Pass |  | Measured 2026-08-20 while a batch of eight schedules was running; no schedule was stalled by another.
TC-PERF-009 | Lead list pagination under load | Manual (browser developer tools) | Fifty leads per page with sorting by UpdatedAt | Open /leads with page size 50 and measure first paint | Under two seconds on the staging build | Pass
TC-PERF-010 | Search conversations with keyword index | Manual timing against service logs | Ten thousand messages indexed for full text search | GET /api/inbox/search?q=keyword with a selective keyword | Under one second for a selective keyword | Pass
TC-PERF-011 | Agent tool call overhead is bounded | Manual timing against service logs | One agent step that calls a tool and returns | Trigger a run and measure the wall time for one tool step | Under four seconds median | Pass
TC-PERF-012 | Idle connection does not leak memory | Manual observation | Dashboard open for thirty minutes with no interaction | Observe resident memory of the browser tab and the API process | No unbounded growth is observed | Pass
TC-PERF-013 | Report export completes within SLA for a year of data | Manual timing against service logs | One year of kpi_daily rows across five channels | Under twenty seconds for a full-year CSV export | 14 s | Pass
TC-PERF-014 | Webhook ingestion holds up under a burst | Manual (load script) | Fifty webhook calls submitted within one second | No HTTP 5xx and no dropped message under the burst | 0 errors, 0 dropped | Pass
TC-PERF-015 | Notification delivery latency from event to unread badge | Manual timing against service logs | An escalation event on a conversation | Under three seconds from escalation to the unread badge updating | 1.8 s | Pass
TC-PERF-016 | PDF render time for a ten-page brochure | Manual (job centre dialog) | A brochure template with ten content sections | Under twenty seconds to a ready PDF | 16 s | Pass