## 1. Overview
[AI-driven marketing and Sales automation system for Hocba company] — Requirements Traceability Workbook
Version 1.0 ¦ Last updated: [08/09/2026]
HOW TO USE THIS WORKBOOK
This workbook has 9 sheets. Fill each sheet when the corresponding artefact is ready.
Sheet 1 (this sheet): auto-calculated summary — formulas pull from other sheets.
Sheets 2–9: one artefact per sheet. Headers are pre-set; add data rows below row 3.
Gray italic rows = guidance / example — DELETE before distributing.
Dropdown validations are pre-configured in each sheet — use them to ensure consistency.
Color coding: BLUE header = primary key column ¦ AMBER = guidance row ¦ ALT rows = light blue
Summary Statistics
Total Features (FT) | Features Specified | Open Issues | Business Rules

## 2. Use Case List
UC ID | UC Name | Primary Actor | Secondary Actor(s) | Precondition (brief) | Postcondition (brief) | Related Feature (FT) | Related Scenario (SC) | Priority | Status | Notes
UC-01 | System Login | User | Auth Service | User has a registered account | JWT token issued, user authenticated successfully | FT-01 | SC-05 | High | Defined
UC-02 | Two-Factor Authentication (2FA) | User | Auth Service | User has enabled TOTP 2FA | 2FA verified, login session granted authorization | FT-02 | SC-05 | High | Defined
UC-03 | Password Recovery | User | Auth Service | User forgot password | OTP code sent via Email, password reset | FT-03 | SC-05 | High | Defined
UC-04 | Staff Account Management | Admin | Identity DB | Admin has access to Admin Panel | Staff profile created/edited/deleted | FT-04 | SC-05 | Medium | Defined
UC-05 | Role-Based Access Control (RBAC) | Admin | Identity DB | Admin has access to Admin Panel | RBAC permissions applied to user | FT-05 | SC-05 | High | Defined
UC-06 | API Key Management | Admin | Auth Service | Admin has access to Admin Panel | API key created with SHA-256 hash | FT-06 | SC-05 | High | Defined
UC-07 | Audit Log Lookup | Admin | Audit Logger | Admin has access to Admin Panel | User actions and IP information queried | FT-08 | SC-05 | High | Defined
UC-08 | Pancake Connection Configuration | Admin / Sales Lead | Pancake API | Admin/Sales Lead has valid Pancake credentials | Tenant's Webhook and AccessToken saved | FT-09 | SC-01 | High | Defined
UC-09 | Multichannel Message Ingestion | Customer | Pancake API, Message DB | Customer sends a comment/message | Raw message collected and parsed | FT-10 | SC-01 | High | Defined | Actual mechanism: polling via Pancake REST API (every 10s), not webhook. Currently only the Zalo channel is confirmed working live
UC-10 | View Unified Inbox | Sale Agent | Inbox DB, SignalR Hub | Sale agent opens the unified inbox | Unified inbox loaded, sorted by priority | FT-11 | SC-01 | High | Defined
UC-11 | Advanced Conversation Filtering | Sale Agent | Inbox DB | Sale agent is on the chat screen | Conversations filtered by platform/status | FT-12 | SC-01 | Medium | Defined
UC-12 | Send Reply Message | Sale Agent | Pancake API | Sale agent enters text or image | Message sent to the customer via Pancake | FT-13 | SC-01 | High | Defined
UC-13 | Change Conversation Status | Sale Agent | Inbox DB | Sale completes or escalates support | Status changed to Resolved/Pending/Escalated | FT-14 | SC-01 | High | Defined
UC-14 | Knowledge Module Management | QA Admin / Sales Lead | KB DB | QA/Sales Lead has KB editing rights | KB modules (FAQ, Pricing) CRUD completed | FT-16 | SC-05 | Medium | Defined
UC-15 | KB Version Tracking | QA Admin | KB DB | QA edits KB content | Revision logged, version incremented | FT-17 | SC-05 | Medium | Defined
UC-16 | Deploy & Sync Vectors | QA Admin | Qdrant DB | QA deploys a draft KB | KB content embedded and stored in Qdrant | FT-18 | SC-05 | High | Defined
UC-17 | Rollback to Previous KB Version | QA Admin | Qdrant DB | Current KB version has low accuracy | Version rolled back, active index updated | FT-19 | SC-05 | Medium | Defined
UC-18 | KB Test-Case Set Management | QA Admin | KB DB | QA opens the accuracy evaluation table | Accuracy evaluation test-cases updated | FT-20 | SC-05 | Medium | Defined
UC-19 | Run Accuracy Test | QA Admin | QA Tester, DeepseekAPI | QA triggers the test suite | All test-cases evaluated, accuracy score logged | FT-21 | SC-05 | High | Defined
UC-20 | Automated Advisory Chatbot (RAG) | Customer | Qdrant DB, Chat Agent | Customer asks about courses/FAQ | Answer generated based on Qdrant embeddings | FT-22 | SC-05 | High | Defined
UC-21 | AI Model & Prompt Configuration | Admin | Agent DB | Admin has access to Prompt Panel | Agent configuration (model, system prompt) updated | FT-23 | SC-05 | High | Defined
UC-22 | AI Agent Operations Management | Admin | Agent Controller | Admin opens Agent Hub | Agent started/stopped/restarted | FT-24 | SC-05 | Medium | Defined
UC-23 | Real-time Log Monitoring | Admin | Agent Controller | Admin inspects a specific Agent | Real-time console log streamed | FT-25 | SC-05 | Medium | Defined
UC-24 | Token Tracking & Management | Admin | System Monitor | Token usage data available | Token spending ledger updated, quota checked | FT-27 | SC-05 | High | Defined
UC-25 | AI Suggested Reply Draft | Sale Agent | Sale Assist DB | Incoming customer message | AI draft generated, max 80 words | FT-28 | SC-02 | High | Defined
UC-26 | AI Conversation Summary | Sale Agent | Sale Assist DB | Conversation has > 10 messages | AI summary generated and shown in sidebar | FT-29 | SC-02 | Medium | Defined
UC-27 | Lead Info Sidebar | Sale Agent | CRM DB | Sale agent views conversation | Lead info, score, activity displayed | FT-30 | SC-02 | Medium | Defined
UC-28 | AI Product Upsell Suggestion | Sale Agent | CRM DB | Lead is near purchase stage | Upsell suggestion pushed to sidebar | FT-31 | SC-02 | Medium | Defined
UC-29 | Quick Reply Template Library | Sale Agent | CRM DB | Sale agent is in the chat window | Quick template selected and inserted | FT-32 | SC-02 | Medium | Defined
UC-30 | SLA Wait-Time Alert | System | SignalR Hub | Conversation wait time > 5/10 minutes | SLA alert triggered on screen | FT-33 | SC-02 | High | Defined | Shown via the general Notification Center; no dedicated SLA threshold/label yet
UC-31 | View Lead List as Kanban | Sale Agent | CRM DB | Sale agent opens CRM Pipeline | Kanban lead list board loaded | FT-34 | SC-06 | Medium | Defined
UC-32 | Detailed Lead Profile Management | Sale Agent | CRM DB | Sale agent opens a lead profile | Timeline, touchpoints, call notes CRUD saved | FT-35 | SC-06 | Medium | Defined
UC-33 | Content Trend Scanning | System | Content Agent, Scraper | Automated schedule (every Monday) OR Marketing Lead clicks manual "Scan" button | Trend report generated and saved; push notification via SignalR/in-app | FT-37 | SC-03 | High | Defined
UC-34 | Content Brief Management | Marketing Lead | Content DB | Strategy already defined by Marketing Lead | Content brief CRUD saved | FT-38 | SC-03 | Medium | Defined
UC-35 | Automated Content Draft Generation | Marketing Lead | Content Agent | Content brief saved or defined | Platform-specific draft (TikTok, FB, Reels) generated | FT-39 | SC-03 | Medium | Defined
UC-36 | View Content Calendar | Marketing Lead | Content DB | Marketing Lead opens calendar | Calendar with scheduled posts loaded | FT-40 | SC-03 | Medium | Defined
UC-37 | Automated Post Scheduling | System | Content Agent, Scheduler | Content approved and scheduled | Post published during the platform's golden hour | FT-41 | SC-03 | High | Defined
UC-38 | Document Template Library Management | Sale Agent | Docs DB | Sale agent opens the template library | Document templates (quotes, brochures) CRUD | FT-42 | SC-02 | Medium | Defined
UC-39 | Automated PDF Quote Generation | Sale Agent | Docs Agent, PDF Engine | Sale agent requests a quote | QuestPDF quote generated in < 30 seconds | FT-43 | SC-02 | High | Defined
UC-40 | View & Preview Documents | Sale Agent | Docs Agent | Document has been generated | Document rendered and preview displayed | FT-44, FT-45 | SC-02 | Medium | Defined
UC-41 | Send Document & Track | Sale Agent | Pancake API, Docs Agent | Document link sent to customer | Logged, read-confirmation when customer opens it | FT-46 | SC-02 | Medium | Defined
UC-42 | KPI Reporting Dashboard | MKT | Analytics DB | PM opens the KPI Dashboard | Aggregate metrics (Lead, CPL) loaded | FT-47 | SC-04 | High | Defined
UC-43 | Conversion Funnel Report | MKT | Analytics DB | PM selects the conversion funnel section | Stage-by-stage conversion rate displayed | FT-48 | SC-04 | Medium | Defined | Actual stage names in code: Lead → DM → Reply → Conversion
UC-44 | Sale & AI Performance Report | MKT | Analytics DB | PM selects the performance section | Accuracy, latency, AI draft usage rate displayed | FT-49 | SC-04 | Medium | Defined
UC-45 | Export PDF/Excel Report | MKT | Analytics DB | PM clicks the export button | Report file generated and downloaded | FT-50 | SC-04 | Medium | Defined | Currently only PDF and CSV are supported; Excel (.xlsx) not yet available
UC-46 | CPL Spike Alert | System | Notification DB, Report Agent, Analytics DB | Daily KPIs aggregated | In-app notification sent via SignalR if CPL rises > 150% (z-score + 1.5x baseline) | FT-51 | SC-04 | High | Defined
UC-47 | AI Agent Plan Approval | Admin / Sales Lead | Agent Controller | AI Agent proposes a plan/action | Plan approved/rejected, action executed/canceled | FT-24, FT-26 | SC-05 | High | Defined
UC-48 | In-App Notification System | User | Notification DB, SignalR Hub | Notifications exist | User views, marks as read, configures notification preferences | FT-52 | SC-05 | Medium | Defined
UC-49 | AI Self-Learning Knowledge Suggestion | QA Admin | KB DB, Chat Agent | AI detects a knowledge gap from conversations | Suggestion auto-created; QA can approve/reject with content edits | FT-22 | SC-05 | Medium | Defined
UC-50 | Skill File Library Management | Admin | Agent DB | Admin opens Skill Panel | Reusable .md skill files created/edited/deleted | FT-53 | SC-05 | Low | Defined
UC-51 | Pixel Agents Office Monitoring Space | Admin / Ops | Agent Controller, SignalR Hub | Admin/Ops accesses Agents Space | Pixel diagram shows real-time Agent status (running/error), task queue, event log updated every 5 seconds | FT-24, FT-25 | SC-05 | Medium | Defined
UC-52 | LLM Provider & Vector Embedding Configuration | Admin | Identity DB, Qdrant DB | Admin has access to the AI configuration panel | LLM provider (Claude, OpenAI) declared/CRUD, base URL, price per 1M tokens, Vector Embedding configuration for KB, and API Key rotation | FT-07 | SC-05 | High | Defined
UC-53 | Lead Forecasting | Sales Lead | Analytics DB, Forecaster (ML.NET) | PM/Sales Lead opens the overview Dashboard | Chart forecasting Lead volume for the next 7 days shown with upper/lower bounds based on historical time-series analysis | FT-47 | SC-04, SC-06 | Medium | Defined
UC-54 | Move Lead Stage to Won/Lost | Sale Agent | CRM DB | Sale agent views lead profile | Lead stage manually updated to won or lost | FT-54 | SC-06 | Medium | Defined

## 3. Feature Traceability
Feature Traceability Matrix
SRS FT ID | Feature Name | V&S Source (FE) | Module | Related UC(s) | Related Scenario(s) | Data Entities | NFR IDs | Business Rules | Test Case ID(s) | Owner | Sprint | Status | Notes
FT-01 | Authentication & Identity | FE-01 | Admin | UC-01 | SC-05 | User, RefreshToken | NFR-SEC-01 | BR-29, BR-30 | TC-FT01-01 | Admin | Sprint 1 | Defined
FT-02 | 2FA Verification | FE-01 | Admin | UC-02 | SC-05 | User | NFR-SEC-01 | BR-29 | TC-FT02-01 | Admin | Sprint 1 | Defined
FT-03 | Password Recovery Service | FE-01 | Admin | UC-03 | SC-05 | User | NFR-SEC-01 | BR-30 | TC-FT03-01 | Admin | Sprint 1 | Defined
FT-04 | Tenant Staff Directory | FE-01 | Admin | UC-04, UC-70 | SC-05 | User | NFR-SEC-02 | BR-30 | TC-FT04-01 | Admin | Sprint 1 | Defined
FT-05 | Role Permission Resolver | FE-01 | Admin | UC-05 | SC-05 | Role, Permission, RolePermission | NFR-SEC-01 | BR-30 | TC-FT05-01 | Admin | Sprint 1 | Defined
FT-06 | API Keys Authentication | FE-01 | Admin | UC-06 | SC-05 | ApiKey | NFR-SEC-01 | BR-29 | TC-FT06-01 | Admin | Sprint 1 | Defined
FT-07 | Tenant Variables Settings | FE-01 | Admin | UC-07, UC-69 | SC-05 | Tenant, Settings, LlmConfig, EmbeddingConfig | NFR-SEC-02 | BR-09 | TC-FT07-01 | Admin | Sprint 1 | Defined
FT-08 | Security Activity Auditor | FE-01 | Admin | UC-08 | SC-05 | AuditLog | NFR-SEC-01 | BR-01 | TC-FT08-01 | Admin | Sprint 1 | Defined
FT-09 | Pancake Connection Setup | FE-02 | Inbox | UC-09, UC-70 | SC-01, SC-05 | PancakeConfig | NFR-PER-01 | BR-01 | TC-FT09-01 | Admin | Sprint 1 | Defined
FT-10 | Multichannel Ingestor | FE-02 | Inbox | UC-10 | SC-01 | Message, Conversation | NFR-PER-01 | BR-04 | TC-FT10-01 | Admin | Sprint 1 | Defined
FT-11 | Message Intent Classifier | FE-02 | Inbox | UC-11 | SC-01 | Message | NFR-PER-02 | BR-33 | TC-FT11-01 | QA | Sprint 1 | Defined
FT-12 | Unified Inbox UI | FE-02 | Inbox | UC-12 | SC-01 | Conversation, Message | NFR-USA-01 | BR-14 | TC-FT12-01 | Sale | Sprint 1 | Defined
FT-13 | Conversation Filter Engine | FE-02 | Inbox | UC-13 | SC-01 | Conversation | NFR-USA-01 | BR-14 | TC-FT13-01 | Sale | Sprint 1 | Defined
FT-14 | Thread Assignment Manager | FE-02 | Inbox | UC-14 | SC-01 | Conversation | NFR-USA-01 | BR-16 | TC-FT14-01 | Sale | Sprint 1 | Defined
FT-15 | Outbound Response Dispatcher | FE-02 | Inbox | UC-15 | SC-01 | Message | NFR-PER-01 | BR-31 | TC-FT15-01 | Sale | Sprint 1 | Defined
FT-16 | Lifecycle State Controller | FE-02 | Inbox | UC-16 | SC-01 | Conversation | NFR-USA-02 | BR-15 | TC-FT16-01 | Sale | Sprint 1 | Defined
FT-17 | Out-of-Hours Auto Responder | FE-02 | Inbox | UC-17 | SC-01 | Message | NFR-PER-01 | BR-02 | TC-FT17-01 | System | Sprint 1 | Defined
FT-18 | Comment Auto PM Invitation | FE-02 | Inbox | UC-74 | SC-01 | Message | NFR-PER-02 | BR-03 | TC-FT18-01 | System | Sprint 1 | Defined
FT-19 | Contact Deduplication Merge | FE-02 | Inbox | UC-18 | SC-01 | Contact, ContactExternalId | NFR-PER-02 | BR-04 | TC-FT19-01 | System | Sprint 1 | Defined
FT-20 | FAQ Knowledge Modules | FE-06 | KB | UC-19 | SC-05 | KbModule, KbVersion | NFR-SUP-01 | BR-06 | TC-FT20-01 | QA | Sprint 1 | Defined
FT-21 | KB Version History Tracker | FE-06 | KB | UC-20 | SC-05 | KbVersion | NFR-SUP-01 | BR-06 | TC-FT21-01 | QA | Sprint 1 | Defined
FT-22 | Vector Embeddings Qdrant Sync | FE-06 | KB | UC-21 | SC-05 | KbVersion | NFR-PER-02 | BR-05, BR-07 | TC-FT22-01 | QA | Sprint 1 | Defined
FT-23 | KB Active Version Rollback | FE-06 | KB | UC-22 | SC-05 | KbVersion | NFR-SUP-01 | BR-07 | TC-FT23-01 | QA | Sprint 1 | Defined
FT-24 | Test Case Collection CRUD | FE-06 | KB | UC-23 | SC-05 | KbTestCase | NFR-SUP-01 | BR-05 | TC-FT24-01 | QA | Sprint 1 | Defined
FT-25 | Accuracy Test Runner Service | FE-06 | KB | UC-24 | SC-05 | KbTestCase, KbVersion | NFR-PER-02 | BR-05 | TC-FT25-01 | QA | Sprint 1 | Defined
FT-26 | Chatbot RAG Assistant Engine | FE-06 | KB | UC-25, UC-64 | SC-05 | Message, Conversation | NFR-PER-02 | BR-33 | TC-FT26-01 | Customer | Sprint 1 | Defined
FT-27 | System Prompts Configuration | FE-06 | Agent | UC-26 | SC-05 | Agent | NFR-SUP-01 | BR-08 | TC-FT27-01 | Admin | Sprint 2 | Defined
FT-28 | Agent Runtime Controller | FE-06 | Agent | UC-27, UC-59, UC-68 | SC-05 | Agent, AgentSession | NFR-PER-02 | BR-08 | TC-FT28-01 | Admin | Sprint 2 | Defined
FT-29 | gRPC Console Real-time Logs | FE-06 | Agent | UC-28, UC-68 | SC-05 | AgentSession | NFR-USA-02 | BR-10 | TC-FT29-01 | Admin | Sprint 2 | Defined
FT-30 | AI Agent Plan Approval | FE-06 | Agent | UC-59 | SC-05 | Agent | NFR-SEC-01 | BR-08 | TC-FT30-01 | Admin | Sprint 2 | Defined
FT-31 | Cost Quota Monthly Ledger | FE-06 | Agent | UC-29 | SC-05 | Agent, LlmCostEntry | NFR-SEC-02 | BR-09, BR-34 | TC-FT31-01 | Admin | Sprint 2 | Defined
FT-32 | Suggestion Reply Draft panel | FE-04 | Sale | UC-30 | SC-02 | Message | NFR-PER-02 | BR-12, BR-13 | TC-FT32-01 | Sale | Sprint 2 | Defined
FT-33 | Long Conversation Summarizer | FE-04 | Sale | UC-31 | SC-02 | Conversation | NFR-PER-02 | BR-12 | TC-FT33-01 | Sale | Sprint 2 | Defined
FT-34 | Context Sidebar Lead Info | FE-04 | Sale | UC-32 | SC-02 | Lead, LeadActivity | NFR-USA-01 | BR-15 | TC-FT34-01 | Sale | Sprint 2 | Defined
FT-35 | Upsell Product Promoter | FE-04 | Sale | UC-33 | SC-02 | Lead | NFR-PER-02 | BR-15 | TC-FT35-01 | Sale | Sprint 2 | Defined
FT-36 | Quick Templates Selector | FE-04 | Sale | UC-34 | SC-02 | QuickReplyTemplate | NFR-USA-01 | BR-13 | TC-FT36-01 | Sale | Sprint 2 | Defined
FT-37 | SLA Breach Alert Dispatcher | FE-04 | Sale | UC-35 | SC-02 | Conversation | NFR-SEC-02 | BR-14 | TC-FT37-01 | System | Sprint 2 | Defined
FT-38 | Lead Scoring Weight Rules | FE-03 | CRM | UC-36 | SC-06 | LeadScoringRule | NFR-SUP-01 | BR-15 | TC-FT38-01 | Admin | Sprint 2 | Defined
FT-39 | Lead Pipeline Kanban View | FE-03 | CRM | UC-37 | SC-06 | Lead | NFR-USA-01 | BR-15 | TC-FT39-01 | Sale | Sprint 2 | Defined
FT-40 | Lead Activity Log Manager | FE-03 | CRM | UC-38 | SC-06 | LeadActivity, Lead | NFR-USA-02 | BR-15 | TC-FT40-01 | Sale | Sprint 2 | Defined
FT-41 | Round-Robin Assignment Engine | FE-03 | CRM | UC-75 | SC-06 | Lead, User | NFR-PER-01 | BR-16, BR-18 | TC-FT41-01 | System | Sprint 2 | Defined
FT-42 | Lead Profile Dedup Merger | FE-03 | CRM | UC-39 | SC-06 | Contact, ContactExternalId | NFR-PER-02 | BR-04 | TC-FT42-01 | System | Sprint 2 | Defined
FT-43 | Drip Sequence Campaign Setup | FE-03 | CRM | UC-40 | SC-06 | DripSequence | NFR-SUP-01 | BR-17 | TC-FT43-01 | Admin | Sprint 2 | Defined
FT-44 | Drip Sequence Message Sender | FE-03 | CRM | UC-41 | SC-06 | Message, Conversation | NFR-PER-01 | BR-17 | TC-FT44-01 | System | Sprint 2 | Defined
FT-45 | Public Live Chat Widget | FE-02 | Inbox | UC-42 | SC-01 | Message, Conversation | NFR-PER-01 | BR-03 | TC-FT45-01 | Customer | Sprint 2 | Defined
FT-46 | Public FAQ Support Page | FE-02 | Inbox | UC-43 | SC-01 | KbModule, KbVersion | NFR-PER-01 | BR-33 | TC-FT46-01 | Customer | Sprint 2 | Defined
FT-47 | Weekly Competitor Scraper | FE-05 | Content | UC-44 | SC-03 | ContentBrief | NFR-PER-01 | BR-19, BR-20 | TC-FT47-01 | System | Sprint 2 | Defined
FT-48 | Content Brief Manager | FE-05 | Content | UC-45 | SC-03 | ContentBrief | NFR-SUP-01 | BR-20 | TC-FT48-01 | Marketer | Sprint 2 | Defined
FT-49 | Platform Specific Drafter | FE-05 | Content | UC-46 | SC-03 | ContentItem | NFR-PER-02 | BR-21 | TC-FT49-01 | Marketer | Sprint 2 | Defined
FT-50 | Editorial Calendar UI | FE-05 | Content | UC-47 | SC-03 | ContentSchedule | NFR-USA-01 | BR-21 | TC-FT50-01 | Marketer | Sprint 2 | Defined
FT-51 | Automated Publishing Job | FE-05 | Content | UC-48 | SC-03 | ContentSchedule | NFR-PER-01 | BR-21, BR-32 | TC-FT51-01 | System | Sprint 2 | Defined
FT-52 | PDF Template Library CRUD | FE-07 | Docs | UC-49 | SC-02 | DocumentTemplate | NFR-SUP-01 | BR-23 | TC-FT52-01 | Sale | Sprint 2 | Defined
FT-53 | Personalized Proposal Render | FE-07 | Docs | UC-50 | SC-02 | GeneratedDocument | NFR-PER-01 | BR-22, BR-23 | TC-FT53-01 | Sale | Sprint 2 | Defined
FT-54 | Demo Slide & Brochure Render | FE-07 | Docs | UC-51 | SC-02 | GeneratedDocument | NFR-PER-01 | BR-22, BR-23 | TC-FT54-01 | Sale | Sprint 2 | Defined
FT-55 | Local Document Previewer | FE-07 | Docs | UC-51 | SC-02 | GeneratedDocument | NFR-USA-01 | BR-22 | TC-FT55-01 | Sale | Sprint 2 | Defined
FT-56 | Link Dispatch Tracker | FE-07 | Docs | UC-52 | SC-02 | GeneratedDocument | NFR-SEC-02 | BR-22 | TC-FT56-01 | Sale | Sprint 2 | Defined
FT-57 | Omnichannel KPI Dashboard | FE-08 | Analytics | UC-53, UC-71 | SC-04, SC-06 | KpiDaily | NFR-USA-01 | BR-25 | TC-FT57-01 | MKT | Sprint 2 | Defined
FT-58 | Funnel & Conversion forecast | FE-08 | Analytics | UC-54 | SC-04 | KpiDaily | NFR-PER-02 | BR-25 | TC-FT58-01 | MKT | Sprint 2 | Defined
FT-59 | Agent & Assist efficiency KPI | FE-08 | Analytics | UC-55 | SC-04 | KpiDaily | NFR-USA-01 | BR-25 | TC-FT59-01 | MKT | Sprint 2 | Defined
FT-60 | Automated Telegram Schedule | FE-08 | Analytics | UC-56 | SC-04 | KpiDaily | NFR-PER-01 | BR-25 | TC-FT60-01 | MKT | Sprint 2 | Defined
FT-61 | Analytical PDF/Excel exporter | FE-08 | Analytics | UC-57 | SC-04 | KpiDaily | NFR-PER-01 | BR-25 | TC-FT61-01 | MKT | Sprint 2 | Defined
FT-62 | CPL Daily Spikes Monitor | FE-08 | Analytics | UC-58 | SC-04 | KpiDaily | NFR-SEC-02 | BR-24, BR-25 | TC-FT62-01 | System | Sprint 2 | Defined
FT-63 | Chat Scenario Manager | FE-02 | Inbox | UC-60 | SC-01 | ChatScenario | NFR-USA-01 | BR-14 | TC-FT63-01 | Admin | Sprint 2 | Defined
FT-64 | Competitor Tracking Service | FE-05 | Content | UC-61 | SC-03 | CompetitorSource, CompetitorPost | NFR-PER-01 | BR-19 | TC-FT64-01 | Marketer | Sprint 2 | Defined
FT-65 | Conversation Labels & Notes | FE-02 | Inbox | UC-62 | SC-01 | ConversationLabel, ConversationNote | NFR-USA-01 | BR-14 | TC-FT65-01 | Sale | Sprint 2 | Defined
FT-66 | In-App Notifications | FE-01 | Admin | UC-63 | SC-05 | Notification | NFR-USA-02 | BR-01 | TC-FT66-01 | System | Sprint 2 | Defined
FT-67 | Skill File Manager | FE-06 | Agent | UC-65 | SC-05 | SkillFile | NFR-SUP-01 | BR-08 | TC-FT67-01 | Admin | Sprint 2 | Defined
FT-68 | Meta Business Channel Setup | FE-02 | Inbox | UC-66 | SC-01 | MetaConnection, MetaAsset | NFR-SEC-01 | BR-01 | TC-FT68-01 | Admin | Sprint 2 | Defined
FT-69 | AI Image Prompt Generator | FE-05 | Content | UC-67 | SC-03 | ContentItem | NFR-PER-02 | BR-21 | TC-FT69-01 | Marketer | Sprint 2 | Defined
FT-70 | Lead Stage Lifecycle Controller | FE-03 | CRM | UC-72 | SC-06 | Lead, LeadActivity | NFR-USA-01 | BR-15 | TC-FT70-01 | Sale | Sprint 2 | Defined
FT-71 | Product & Service Catalog Setup | FE-07 | Docs | UC-73 | SC-02 | Product | NFR-SUP-01 | BR-23 | TC-FT71-01 | Admin | Sprint 2 | Defined

## 4. Permission Matrix
Permission Matrix
Add roles as columns. Add feature areas and actions as rows. Use F~Full/E~Edit/R~Read/O-Own/— codes. Apply conditional formatting to colour by code.
Feature Area | Action | Admin | SalesLead | Sale | Marketer | QA
Dashboard | View overview dashboard & summary widgets | R | R | R | R | R
Leads & CRM | View lead list, lead profile & Kanban pipeline | F | F | F | R | R
| Create new lead / edit lead details & notes | F | F | F | — | —
| Delete lead record | F | — | — | — | —
| Reassign lead owner between Sale reps | F | F | — | — | —
Conversations / Inbox | View unified inbox & conversation history | F | F | F | R | R
| Reply / send message to customer | F | F | F | — | —
| Change conversation status (Resolved/Pending/Escalated) | F | F | F | — | —
Sale Assist (AI Draft/Summary) | Use AI-suggested reply draft & conversation summary | F | F | F | — | —
Content & Marketing | View content items & editorial calendar | F | R | R | F | R
| Create / edit content draft (per platform) | F | — | — | F | —
| Approve content before publishing | F | — | — | E | —
| Publish / schedule content to channels | F | — | — | — | —
Documents | View document list & preview generated documents | F | F | F | F | R
| Create document from template / generate quote (PDF) | F | F | F | F | —
| Delete document or template | F | — | — | — | —
Knowledge Base (KB) | View KB modules, articles & version history | F | F | R | F | F
| Create / edit KB content (FAQ, pricing, etc.) | F | F | — | F | F
| Deploy new KB version / rollback to previous version | F | — | — | — | F
Chat Scenarios / Scripts | View chat scenario scripts | F | F | R | F | F
| Create / edit chat scenario scripts | F | F | — | F | F
Agent & Workflow Config | View AI agent list & workflow configuration | F | R | — | R | R
| Configure agent (start / stop / restart / edit prompt) | F | — | — | — | —
Orchestration | View orchestration task graph & execution status | F | E | — | E | R
| Run / trigger orchestration task | F | E | — | E | —
| Approve AI agent's proposed plan/action | F | E | — | — | —
| Manage full orchestration engine configuration | F | — | — | — | —
Analytics & Reports | View KPI dashboard, funnel & performance reports | F | R | R | R | R
| Export report to PDF / CSV | F | — | — | — | —
Jobs / Task Queue | View background job queue & status | F | F | R | F | R
| Manage (retry / cancel / reschedule) background jobs | F | F | — | F | —
System Settings & Channels | View / configure channel & system-wide settings | F | R | — | — | —
LLM Providers | Configure LLM provider, base URL & pricing per 1M tokens | F | — | — | — | —
System Logs | View system & security audit logs | F | — | — | — | —
Prompt Templates & Token Quota | Manage prompt templates & monthly LLM token quota | F | — | — | — | —
Pancake Token | Manage Pancake integration access token | F | F | — | — | —
User & Role Management (RBAC) | Manage staff accounts, roles & permission assignments | F | — | — | — | —
API Keys | Create / revoke API keys | F | — | — | — | —

## 6. Business Rules
Business Rules Register
BR ID | Rule Description | Applies to Feature(s) | Trigger / Condition | Exception Handling | Source / Authority | Status | Owner | Notes
BR-01 | HMAC-SHA256 signature verification must be performed before processing webhook messages from Pancake. | FT-09, FT-10 | Receiving Pancake webhook | Verification failed -> Return error code 401, log audit_logs. | Security Policy | Approved
BR-02 | The center's working hours: 06:00-22:00 GMT+7. Outside this time, ChatAgent will automatically reply to customers. | FT-17 | Message received outside 06:00-22:00 | Auto-reply within 5 seconds. | Business Policy | Approved
BR-03 | Comments with the intention of asking for price/buying must be automatically replied to publicly and inboxed to invite consultation. | FT-45 | Price inquiry comment detected | Auto-reply to cmt and send PM within 30 seconds. | Business Policy | Approved
BR-04 | Customer contact is uniquely identified and merged based on the value pair (platform, external_id). | FT-10, FT-19, FT-42 | Detected existing external_id | Merge chat history into old contact profile. | System Design | Approved
BR-05 | The accuracy score threshold of the Knowledge Base must reach >= 85% to be deployed. | FT-22, FT-24, FT-25 | QA Admin clicks deploy KB version | Deployment blocked if score < 85%. Send alert. | Business Policy | Approved
BR-06 | Deployed Knowledge Base versions on the live system cannot have their content modified (Immutable). | FT-20, FT-21 | Attempt to edit running KB version | System refuses to save. Requires creating a new version. | System Design | Approved
BR-07 | Deploying a new KB must ensure zero-downtime, without interrupting the running AI Agent's conversation sessions. | FT-22, FT-23 | New KB version deployed | Clear old cache, AI Agent receives new version on the next question. | System Design | Approved
BR-08 | AI Agent auto-recovery mechanism: allows auto-restart up to 3 crashes within 5 minutes. | FT-28 | Agent crashes/connection error | Auto-restart, if over 3 times -> Change status to Error + Alert. | System Design | Approved
BR-09 | Monthly LLM API cost quota is strictly controlled per Tenant (Hard cap $200, alert at 80%). | FT-07, FT-31 | API cost calculated in ledger | Cost >= $160 -> Alert; Cost >= $200 -> Stop calling LLM. | Business Policy | Approved
BR-10 | Agent traces must use the standard OpenTelemetry gen_ai.* format for monitoring. | FT-29, FT-30 | Trace log recorded | Record standard telemetry attribute format. | System Design | Approved
BR-11 | AI Orchestrator breaks down weekly/monthly goals through Semantic Kernel. | FT-28 | Orchestration task called | Call via Semantic Kernel planner. | System Design | Approved
BR-12 | SaleAssist assistant's suggested draft messages (AI draft) must be under 80 words and prioritize using Vietnamese. | FT-32, FT-33 | Draft generated | Truncate text if over 80 words. | Business Policy | Approved
BR-13 | AI suggested drafts must not be stored in the official message DB, only returned as temporary text. | FT-32, FT-36 | Draft displayed to Sale | Do not record in messages table until sale clicks send. | System Design | Approved
BR-14 | Customer conversation waiting over 5 minutes without Sale reply will trigger SLA alert. | FT-12, FT-13, FT-37 | Wait time > 5 minutes | Push notification to dashboard and team Telegram. | Business Policy | Approved
BR-15 | Lead score is categorized by threshold: >=70 is Hot, 30-69 is Warm, <30 is Cold. | FT-16, FT-34, FT-35, FT-38, FT-39, FT-40 | Lead score updated | Update CRM Stage automatically. | Business Policy | Approved
BR-16 | Hot Lead must be automatically assigned to active Sale via Round-robin algorithm. | FT-14 | Lead status updated to Hot | Auto-assign and notify Sale to receive in < 2 minutes. | System Design | Approved
BR-17 | Cold Lead with no activity for 7 consecutive days will automatically receive a nurturing drip sequence. | FT-43, FT-44 | Lead inactive > 7 days | Send auto-nurturing Sequence message via incoming channel. | Business Policy | Approved
BR-18 | Assigned Hot Lead with no Sale response in 24h will be auto-revoked and reassigned to another Sale. |  | Over 24h no response | Reassigned. Notify old Sale and team leader. | Business Policy | Approved
BR-19 | Content Scraper assistant automatically scans competitor trends at 07:00 GMT+7 every Monday. | FT-47 | Monday 07:00 GMT+7 | Scan minimum 4 sources (TikTok, YouTube) for trends. | System Design | Approved
BR-20 | Content Brief idea summaries are traced under the prefix [trend:{weekOf}] to avoid duplication. | FT-47, FT-48 | Brief initiated from trend | Check duplication before insert. | System Design | Approved
BR-21 | Content plan is automatically scheduled to post during the golden hour of each platform. | FT-49, FT-50, FT-51 | Post approved | Schedule posting during highest traffic hour. | Business Policy | Approved
BR-22 | Auto-generated PDF/Brochure document time must be under 30 seconds. Use local disk as fallback when MinIO fails. | FT-53, FT-54, FT-55, FT-56 | Request to render PDF | Auto-save to local disk temporarily if storage is down. | System Design | Approved
BR-23 | PDF document render requests missing required parameters (metadata keys) will return error code 422. | FT-52, FT-53, FT-54 | Missing info field key | Return list of missing fields. | System Design | Approved
BR-24 | Immediate alert sent if today's CPL (Cost Per Lead) increases >150% compared to 7-day average. | FT-62 | Daily KPI calculated | Send urgent alert via Admin Telegram channel. | Business Policy | Approved
BR-25 | KPI daily rollup task runs automatically at 00:30 GMT+7 daily. | FT-57..FT-62 | At 00:30 GMT+7 | Fill daily rollup data into kpi_daily table. | System Design | Approved
BR-26 | Security JWT Token has a Time-To-Live (TTL) of 15 minutes, Refresh Token is stored in HttpOnly cookie. | FT-01 | Issue Login Token | Token expires after 15m, auto-refresh silently. | Security Policy | Approved
BR-27 | Temporarily lock employee account for 30 minutes if wrong password entered 5 consecutive times. | FT-01, FT-04 | Enter wrong pass 5th time | Lock login, record event in audit log. | Security Policy | Approved
BR-28 | Personal Identifiable Information (PII) must be encrypted before sending to LLM. Raw chat log files are periodically deleted after 30 days. | FT-10, FT-35 | Message about to be sent | Mask customer phone/email before sending. | Legal/Compliance | Approved
BR-29 | High-risk Agent actions (posting new article) must be paused in 'pending_review' status. | FT-27, FT-51 | Agent attempts to post article | Await manual moderation and approval from manager. | Business Policy | Approved
BR-30 | Low-risk actions (chatting with customers, updating lead score) are automatically executed directly. | FT-10, FT-26 | Agent chats or updates score | Execute directly and record activity log. | Business Policy | Approved
BR-31 | Planner Agent has monthly API budget hard-capped at $200/tenant, soft alert at 80%. | FT-31 | Token cost calculated in ledger | Exceed $160 SignalR alert, exceed $200 stop planning. | Business Policy | Approved
BR-32 | Auto-replanning frequency is limited to maximum 1 time per 10 minutes per tenant. | FT-28 | Continuous urgent events | Rate-limit check blocks consecutive re-plan requests. | System Design | Approved
BR-33 | All Agent-to-Agent inter-calls must go through Orchestrator gateway to record audit trace. | FT-28 | Agent calls subtask of another Agent | Trace log recorded in agent_traces, direct cross gRPC calls forbidden. | System Design | Approved

## 7. NFR Tracker
Non-Functional Requirements Tracker
NFR ID | Category | Requirement | Condition / Context | Target Value | Test Method | Tool | Measured Result | Test Status | Owner | Sprint | Notes
NFR-PER-01 | Performance | Response time for receiving webhook from Pancake API | Normal load (100 concurrent requests) | < 2.0 seconds | Load test | k6 / JMeter | 1.2 seconds | Passed | System | Sprint 1 | Ensure Pancake does not timeout
NFR-PER-02 | Performance | AI Agent draft response generation time (AI Draft) | User opens a single conversation | < 2.0 seconds | End-to-end telemetry measurement | OpenTelemetry | 1.5 seconds | Passed | QA | Sprint 2 | Use Claude Sonnet 4.6
NFR-SEC-01 | Security | Time to live (TTL) of JWT Access Token | Active logged-in user | 15 minutes | Check token configuration | Postman / Code review | 15 minutes | Passed | Admin | Sprint 1 | Token automatically expires and silent refresh
NFR-SEC-02 | Security | Encrypt Tenant's sensitive information (Pancake Access Token) | Store connection info in DB | Must not appear in plaintext | Check raw database queries | SSMS / SQL query | Encrypted with AES-256 | Passed | Admin | Sprint 1 | Use system's AesEncryptor
NFR-USA-01 | Usability | Unified Inbox UI page load time | Normal office network | < 1.0 seconds | Measure web page load performance | Chrome DevTools | 0.8 seconds | Passed | Sale | Sprint 1 | Applied pagination and lazy load
NFR-USA-02 | Usability | Load embedded Metabase KPI graphical report (BI iframe) | When opening the analytics tab | < 3.0 seconds | Measure iframe load time | Chrome DevTools | 2.5 seconds | Passed | PM | Sprint 2 | Load directly via Metabase JWT URL
NFR-SUP-01 | Supportability | Deploy new Knowledge Base (KB) without dropping connections | AI Agent is in a consultation session | 0 chat sessions interrupted (Zero-downtime) | Run simulated deploy test while chatting | Smoke tests | 0 sessions interrupted | Passed | QA | Sprint 1 | Use cache invalidation
NFR-REL-01 | Reliability | AI Agent auto-recovery time (Auto-restart) | Agent crashes or gRPC timeout | < 10 seconds | Simulate Agent process crash | gRPC CLI / Logs test | 4.2 seconds | Passed | Admin | Sprint 2 | Auto-restart max 3 times/5 mins
NFR-LEG-01 | Legal / Privacy | Periodic cleanup of raw message data to protect PII | Message data older than 30 days | Clear daily | Check job scheduler log | SQL Server Agent | Successfully deleted | Passed | System | Sprint 1 | Complies with BR-28

## 8. Open Issues
Open Issues Log
Issue ID | Description | Type | Raised by | Owner (must answer) | Status | Priority | Deadline | Affected Area | Resolution / Decision | Resolved Date
OI-01 | EF Core treats a client-assigned Guid key as an auto-generated key → the ingestor appends an error message when saving | Bug | Dev / test suite | NguyenTung309 | Closed | High |  | Infrastructure / EF Core | Configured the client-assigned Guid key as ValueGeneratedNever | 2026-06-02
OI-02 | Solution fails to build: Clawbot.Gateway had its TargetFramework overridden to net10; missing 'using System.Threading.RateLimiting'; PancakeHmacMiddleware calls GetMetadata<bool>(string) invalidly on YARP | Build Error | Dev | NguyenTung309 | Closed | High |  | Gateway / YARP | Retargeted to net8, moved to src/gateway, read RequiresHmac via RouteModel metadata, pinned SDK 8.0.418. Build 0/0 | 2026-06-04
OI-03 | Login flow error — does not run correctly | Bug | Dev | Thanglm240723 | Closed | High |  | Frontend / Auth | Fixed login and the login flow | 2026-06-06
OI-04 | RabbitMQ publish failure caused SaveChanges to throw an error even though the DB transaction had already committed → caller retried incorrectly, causing duplicate data writes | Bug | Code review | NguyenTung309 | Closed | High |  | Messaging / MassTransit | Wrapped DomainEventDispatchInterceptor in try/catch + logging; events are temporarily lost until an outbox is implemented | 2026-06-10
OI-05 | Migration 0013 used the GO command, but the runner executes the whole file as a single SqlCommand → migration fails | Build Error | Code review | NguyenTung309 | Closed | High |  | DB Migrations | Removed GO, split the index on the newly added users column into file 0014 (separate batch) | 2026-06-13
OI-06 | Cross-tenant IDOR security vulnerability: AdminUsersEndpoints update/enable/disable/reset-password did not check tenant (AppUser does not implement ITenantOwned) | Security | Code review | NguyenTung309 | Closed | Critical |  | API / Admin Users | Added a FindInTenantAsync tenant guard across all admin-user endpoints | 2026-06-13
OI-07 | Alerts from IdleConversationAlertJob / AnomalyAlertJob were not saved to the notification center; /api/agents and its toggle did not work due to 8 missing AgentConfig rows; login still allowed users that had been disabled by an admin | Bug | Code review | NguyenTung309 | Closed | Medium |  | Jobs / RBAC / Auth | Wired INotificationPublisher into both jobs, had RbacSeeder seed 8 AgentConfig rows per tenant, and had login check AppUser.IsActive | 2026-06-13
OI-08 | A lead re-warming a second time hit the UNIQUE(sequence_id, lead_id) constraint → message dropped into the dead-letter queue | Bug | Code review | NguyenTung309 | Closed | High |  | Drip / Lead pipeline | LeadBecameWarmConsumer now checks ALL enrollments (not just active ones) before enrolling | 2026-06-13
OI-09 | Pancake API base URL was a placeholder (pages.fm/api/public_api/v1) → returned the web app's HTML shell instead of JSON, breaking every call | Config Error | Live probe / spike | NguyenTung309 | Closed | Critical |  | Channels / Pancake | Changed the base URL to pancake.vn/api/v1 in PancakeConfig, the Resolver, and AgentService appsettings | 2026-06-14
OI-10 | Auto-spam loop: the system replied to its own messages, sending messages continuously | Bug | Dev | Thanglm240723 | Closed | Critical |  | Inbox / Ingestor | Blocked the loop + added an IngestAsync pipeline and ITenantResolver | 2026-06-16
OI-11 | SplitThread returned empty → pagePart was empty, messages could not be sent to Pancake | Bug | Dev | Thanglm240723 | Closed | High |  | Channels / Pancake adapter | Fell back pagePart to cfg.PageId when SplitThread is empty | 2026-06-16
OI-12 | Tests failed to compile: PancakeConfigResolverTests had an orphaned method outside the class; CA1001/CA1725 analyzer warnings | Build Error | CI / build | Thanglm240723 | Closed | Medium |  | Tests | Fixed test syntax, added PancakeAdapterSendTests for SendAsync | 2026-06-16
OI-13 | Incorrect configuration at runtime | Config Error | Dev | Thanglm240723 | Closed | Medium |  | Config | Fixed the configuration | 2026-06-16
OI-14 | Merging the login branch broke things → had to revert entirely | Regression | Dev | thanglm240723 | Closed | High |  | Auth | Reverted the login merge commit | 2026-06-17
OI-15 | Login error caused by a missing DI registration (service could not be resolved at runtime) | Bug | Dev | Thanglm240723 | Closed | High |  | API / DI container | Registered the missing service(s) fully in DI | 2026-06-17
OI-16 | Could not log in on the dev environment because the tenant and admin account had not been seeded | Config Error | Dev | NguyenTung309 | Closed | High |  | Seed / Auth | Seeded the dev tenant and admin login account as part of the local run process | 2026-06-17
OI-17 | Incorrect configuration on the working branch | Config Error | Dev | Thanglm240723 | Closed | Low |  | Config | Fixed the configuration (thang/fix branch) | 2026-06-17
OI-18 | Old authorization policies (legacy perm policies) no longer matched the new permission system → requests were incorrectly blocked | Tech Debt | Dev | NguyenTung309 | Closed | Medium |  | RBAC / Authorization | Migrated legacy policies to permission filters | 2026-06-20
OI-19 | API configuration error and data-pull flow error | Bug | Dev | Thanglm240723 | Closed | Medium |  | API / Config | Fixed the API config and pull bugs | 2026-06-21
OI-20 | Conversation was missing ReopenIfNeeded/Snooze methods; CA1806 analyzer warning from ignoring the TryParse result | Bug | Code review | Thanglm240723 | Closed | Medium |  | Domain / Conversation | Added the 2 missing methods + fixed the TryParse CA1806 issue | 2026-06-23
OI-21 | An admin who was not an inbox member could still send messages / apply labels / add notes (exceeding view-only permissions) | Security | Code review | Thanglm240723 | Closed | High |  | API / Inbox permission | Blocked send/label/note actions for admins who are not members | 2026-06-23
OI-22 | AdminInboxEndpoints had a quote-character encoding error → the source file was corrupted | Build Error | Dev | Thanglm240723 | Closed | Medium |  | API / AdminInboxEndpoints | Fixed the quote-character encoding | 2026-06-23
OI-23 | Audit log was initialized incorrectly; Unassign caused a NullReference; the notes endpoint was missing a parameter | Bug | Code review | Thanglm240723 | Closed | Medium |  | API / Audit + Notes | Fixed the audit log initialization, added null-safety for Unassign, fixed the notes parameters | 2026-06-23
OI-24 | 12 issues from the Spec 15 code review: incorrect regex, missing import, token not saved, conversation not reopening, wrong message direction, missing senderId, wrong copilot ordering, missing delete permission, missing SignalR event, wrong note author, component not wired up | Bug | Code review | Thanglm240723 | Closed | High |  | Full-stack (Agent Hub) | Fixed all issues in a single batch | 2026-06-23
OI-25 | DailySummaryJob called the wrong NotificationRequest constructor, had the wrong direction, and the wrong scope uid → the job failed | Bug | Dev | Thanglm240723 | Closed | High |  | Jobs / Notification | Rewrote DailySummaryJob (correct constructor + LoggerMessage + fixed direction + uid scope) | 2026-06-23
OI-26 | Local schema had drifted; the agents.llm_config_id FK caused a SQL Server cascade-path error when creating the table | Data Issue | Dev | NguyenTung309 | Closed | High |  | DB / run-all.bat | Now always runs an idempotent runtime schema repair; changed the FK to NO ACTION | 2026-06-23
OI-27 | The demo seed could not select a tenant; the repair script was missing SQL Server's required SET options | Config Error | Dev | NguyenTung309 | Closed | Medium |  | Seed / run-all.bat | Parsed the --tenant argument, ensured the tenant exists, passed TenantSlug through sqlcmd, and set the required SET options | 2026-06-23
OI-28 | Runtime error: the scopes_json column does not exist in the api_keys table | Data Issue | Runtime log | NguyenTung309 | Closed | High |  | DB / api_keys | Added an auto-apply EF migration step to run-all.bat | 2026-06-24
OI-29 | Frontend calls to /api/channels/pancake returned 404 (backend used a different route) | Bug | Runtime log | NguyenTung309 | Closed | High |  | API / Channels | Added the /api/channels/pancake route as expected by the frontend | 2026-06-24
OI-30 | The audit-logs page crashed during JSON serialization because the IPAddress field could not be serialized | Bug | Runtime log | NguyenTung309 | Closed | High |  | API / Audit logs | Called IPAddress.ToString() in the projection | 2026-06-24
OI-31 | Frontend calls to /api/kb/modules returned 404 | Bug | Runtime log | NguyenTung309 | Closed | Medium |  | API / Knowledge Base | Added the /api/kb/modules route | 2026-06-24
OI-32 | Planner JSON parsing failed when the LLM returned prose before the markdown block → the plan could not be generated | Bug | Runtime log | NguyenTung309 | Closed | High |  | AI / Planner | Added a fence stripper to handle prose preceding the markdown block | 2026-06-24
OI-33 | Could not run the EF migration because the dotnet-ef tool was not installed on the machine | Environment | Dev | NguyenTung309 | Closed | Medium |  | DevOps / Migrations | Removed the EF migration step, added the scopes_json column to the SQL repair block instead (default '[]') | 2026-06-24
OI-34 | Column name mismatch between SQL (scopes) and EF (scopes_json) on the api_keys table | Data Issue | Dev | NguyenTung309 | Closed | High |  | DB / api_keys | Migration 0033 renamed the column + updated the repair logic in run-all.bat | 2026-06-24
OI-35 | The C# model was missing the PancakeFrom/LastSentBy/Customers records → could not parse the Pancake API response (lost avatar and customer name) | Bug | Dev | Thanglm240723 | Closed | High |  | Channels / Pancake models | Added the missing records to the model | 2026-06-25
OI-36 | Message direction (inbound/outbound) was determined incorrectly; avatar was not saved; inbox name was not updating; there was an incorrect routing bias | Bug | Dev | Thanglm240723 | Closed | High |  | Inbox / Ingestor | Fixed direction detection, saved the avatar, updated the inbox name, removed the routing bias | 2026-06-25
OI-37 | Frontend showed the wrong avatar, name, and alignment for customer messages | Bug | Dev | Thanglm240723 | Closed | Medium |  | Frontend / Chat | Fixed the avatar/name/alignment component | 2026-06-25
OI-38 | Existing conversations were not having their contact metadata (name/avatar/inbox) updated when new data arrived | Bug | Dev | Thanglm240723 | Closed | Medium |  | Inbox / Contact | Added UpdateContactMetadataAsync + TDD tests for direction/avatar/inbox name | 2026-06-25
OI-39 | InboxId could not be resolved for old conversations before renaming; a frontend file had a formfeed character inserted, corrupting the source | Bug | Dev | Thanglm240723 | Closed | Medium |  | Inbox / Frontend | Resolved InboxId before updating, fixed the formfeed corruption | 2026-06-25
OI-40 | Minimal API could not inject ILogger via DI (a minimal API limitation) → the endpoint failed on initialization | Bug | Dev | Thanglm240723 | Closed | Medium |  | API / DI | Resolved ILogger via HttpContext instead | 2026-06-25
OI-41 | The ChatMessageThread file had a broken template literal → frontend build failed | Build Error | CI / build | Thanglm240723 | Closed | High |  | Frontend / Chat | Restored the template literal | 2026-06-25
OI-42 | Only the page configured via an environment variable was polled; other inboxes with tokens still did not receive messages | Bug | Dev | Thanglm240723 | Closed | High |  | Polling / Pancake | Now polls all inboxes that have a token | 2026-06-25
OI-43 | Switching channels did not reset the old activeId and tab → the wrong conversation was shown | Bug | Dev | Thanglm240723 | Closed | Medium |  | Frontend / Inbox | Reset activeId + tabs when switching channels | 2026-06-25
OI-44 | Native runtime binaries bloated the repo, causing pushes to fail | Environment | Dev | Thanglm240723 | Closed | Medium |  | Repo / Git LFS | Tracked with Git LFS, then removed the runtime files from the repo entirely | 2026-06-27
OI-45 | Avatar bug in the chat window | Bug | Dev | Thanglm240723 | Closed | Medium |  | Frontend / Chat | Fixed the chat avatar bug | 2026-06-29
OI-46 | Forms were missing an error state; dangerous actions (changing password, resetting 2FA, deleting tokens/roles/api keys) ran immediately without confirmation; ConversationsPage's fixed height overflowed the layout in mobile landscape | UX / Bug | Code review | NguyenTung309 | Closed | Medium |  | Frontend / Shared UI | Added an error prop + aria-describedby, a shared ConfirmDialog, fixed the layout, and added loading/empty/error states | 2026-07-01
OI-47 | The messages table was missing the attachment_url column → saving messages with files failed | Data Issue | Runtime log | Thanglm240723 | Closed | High |  | DB / messages | Added the column via EnsureRuntimeSchema | 2026-07-02
OI-48 | Adding a prefix to ExternalThreadId caused duplicate conversations to be created | Regression | Dev | Thanglm240723 | Closed | High |  | Inbox / Conversation | Reverted the ExternalThreadId prefix change | 2026-07-02
OI-49 | The 10 req/minute auth rate limit starved the refresh-token flow → users were logged out / got 429 errors | Bug | Runtime log | Thanglm240723 | Closed | High |  | API / Rate limit | Raised the auth rate limit to 30 req/minute | 2026-07-02
OI-50 | Group chat showed the wrong avatar; rich content (audio/video) and document download links were not displayed | Bug | Customer | Thanglm240723 | Closed | Medium |  | Frontend / Chat | Fixed the group chat avatar, rendered rich content, and added download links | 2026-07-02
OI-51 | Sender had no avatar → group chat showed an empty avatar | Bug | Customer | Thanglm240723 | Closed | Low |  | Frontend / Chat | Fell back to the conversation's contact avatar | 2026-07-03
OI-52 | Incorrect assignment bug during message polling | Bug | Dev | Thanglm240723 | Closed | High |  | Polling / Assignment | Fixed the assignment bug during message polling | 2026-07-04
OI-53 | Inbound and outbound tokens used two different sources → sending/receiving mismatched channels | Bug | Dev | Thanglm240723 | Closed | High |  | Channels / Token | Consolidated to using the inbox token for both inbound and outbound | 2026-07-05
OI-54 | CUSTOMER-REPORTED BUG: the left-side chat list had its name + avatar overwritten by the last message sender (including admin/AI) → showed the Zalo/OA owner's name instead of the customer's name; in group chats, the avatar changed with every member who messaged | Bug | Customer | NguyenTung309 | Closed | Critical |  | Polling / ChannelMessageIngestor | Separated conversation_name/avatar from sender_*; computed isOwner before upserting (added the sender_id == page_id condition); added deploy/fix_contact_overwrite.sql to repair corrupted data; contacts self-heal on the next poll | 2026-07-06
OI-55 | Tokens were stored as plaintext in inboxes.encrypted_access_token; the token input field on the frontend silently dropped input; there were 4 parallel token sources (users, pancake_pages dead path, env) | Security | Customer | NguyenTung309 | Closed | High |  | Channels / Token | Standardized: inboxes is now the single source of truth for tokens (page_id + token per channel), consistent encryption, added a token-update endpoint, removed per-salesperson tokens | 2026-07-06
OI-56 | Inbound messages were ingested directly within the poll loop, bypassing RabbitMQ (reported missing by the customer) → did not scale and could easily lose messages on error | Tech Debt | Customer | NguyenTung309 | Closed | Medium |  | Messaging / Polling | Published a ChannelInboundMessageReceived event, added ChannelInboundMessageConsumer (idempotent by external_message_id) | 2026-07-06
OI-57 | Startup race condition: schema check ran while the clawbot DB was not yet online (still recovering) → app crashed | Bug | Runtime log | NguyenTung309 | Closed | High |  | Startup / DB | Now waits for the DB to be online before running the schema check | 2026-07-06
OI-58 | appsettings had Server=localhost, so API/AgentService running on the host silently connected to the local Windows SQL Server with an empty clawbot DB (instead of the SQL Server in Docker) | Config Error | Dev | NguyenTung309 | Closed | Critical |  | Config / DB connection | Pointed it back to localhost,11433 (the SQL Server in Docker) | 2026-07-06
OI-59 | Google Trends RSS changed endpoints: the old daily URL returned 404 → trend scans came back empty | Bug | Runtime log | NguyenTung309 | Closed | Medium |  | Trends / Integration | Switched to /trending/rss, with the parser reading both namespaces | 2026-07-06
OI-60 | Sending messages via the Pancake API v2 failed; senderId was missing | Bug | Dev | Thanglm240723 | Closed | High |  | Channels / Pancake send | Downgraded the URL from v2 to v1 and added senderId | 2026-07-06
OI-61 | CUSTOMER-REPORTED BUG (UX): chat did not auto-scroll to the newest message; long modal forms pushed the Save button off-screen; the 'Try a reply' sandbox overlapped the form; channel names showed the pageId instead of the real name; the leads table showed IDs instead of customer and salesperson names | Bug | Customer | NguyenTung309 | Closed | High |  | Frontend (Inbox/Lead/Agent) | Anchored scroll to the bottom when opening chat, added modal max-height + body scroll, made the sandbox a fixed block, added an inbox-rename field, and joined LeadDto with contacts/users | 2026-07-08
OI-62 | Tenant drift: the poller ingested using a global demo resolver instead of inbox.TenantId → leads were assigned the wrong owner; many records had a NULL inbox_id | Data Issue | Dev | NguyenTung309 | Closed | High |  | Polling / Multi-tenant | Now ingests by inbox.TenantId, the ingestor self-heals NULL inbox_id records, and ran backfill_lead_owners.sql | 2026-07-08
OI-63 | Pancake staleness: the API list v2 returned a stale updated_at, so the watermark skipped messages → conversations did not update | Bug | Khách hàng | NguyenTung309 | Closed | High |  | Polling / Pancake | Now scans the 10 most recent conversations every 60s, bypassing the watermark; added diagnose_pancake_stale.ps1 | 2026-07-08
OI-64 | ChatAgent ignored the tenant's config.SystemPrompt (only the sandbox used it) → the agent replied with the wrong persona | Bug | Dev | NguyenTung309 | Closed | Medium |  | AI / Agent prompt | ChatAgent now reads the tenant's SystemPrompt; applied the guardrail across chat/sandbox/orchestrator | 2026-07-08
OI-65 | Outgoing messages were saved twice (saved locally on send + the poller re-ingesting the echo from the channel) → duplicate messages in the list | Bug | Dev | NguyenTung309 | Closed | High |  | Inbox / Dedup | Applied StripHtml before IsDuplicateAsync; SendAsync now returns the channel's message ID, saved into ExternalMessageId; added fix_duplicate_outbound_echo.sql to remove duplicate rows | 2026-07-09
OI-66 | ParseAsync did not correctly parse Pancake's real webhook format → always returned empty, making the entire webhook path dead code; the comment-reply job called reply_inbox by mistake | Bug | Dev | NguyenTung309 | Closed | Critical |  | Channels / Comment auto-reply | Fixed parsing of {page_id, event_type, data{...}}; added ICommentChannelAdapter (reply_comment + private_replies); resolved from_id via ContactExternalIds | 2026-07-10
OI-67 | LlmConfigResolver did not fall back when the bound config had become inactive → the agent could not call the LLM | Bug | Dev | NguyenTung309 | Closed | High |  | AI / LLM config | Falls back to the oldest active config when the bound config is inactive | 2026-07-11
OI-68 | Plan generation failed when the LLM returned numeric task IDs or invalid JSON | Bug | Dev | NguyenTung309 | Closed | Medium |  | AI / Orchestration | Handled numeric task IDs + added auto-correction for invalid JSON replies, plus tests | 2026-07-11
OI-69 | AI drafts were duplicating: when a customer sent messages in quick succession, pending-approval drafts stacked on top of each other; SaleAssist's 'Approve before sending' toggle was dead — not wired to the real tenant flag | Bug | Dev | NguyenTung309 | Closed | High |  | Chat / Approval gate | Skips auto-reply when a pending_approval draft already exists; synced the toggle with the real tenant flag via an orchestration query | 2026-07-12
OI-70 | The screen froze while waiting for the agent to run; background jobs gave no visibility into status or failures | UX / Bug | Customer | NguyenTung309 | Closed | High |  | Platform / Background jobs | Every LLM call now returns 202 + a jobId; JobRunner runs it in the background (dedicated 'ai' queue, 3 retries), with a notification + deep link to the result; errors are PII-redacted | 2026-07-14
OI-71 | A salesperson sending one manual message permanently turned off the AI; the customer's last message was left hanging with no reply | Bug | Customer | NguyenTung309 | Closed | High |  | AI auto-reply | AI now pauses for a configurable window (default 5 minutes); AiAutoReplyResumeJob scans every minute to re-enable it and answer the pending message; added a regenerate endpoint | 2026-07-17
OI-72 | Failed message sends were not retried, and there was no send-status lifecycle | Bug | Runtime log | NguyenTung309 | Closed | High |  | Outbound delivery | Added FailedMessageRetryService + a retry endpoint, ChatSessionRecoveryService, and pending_send/send_failed statuses | 2026-07-17
OI-73 | The knowledge base could not be retrieved when a tenant had not enabled embedding config → the AI answered with incorrect knowledge | Bug | Dev | NguyenTung309 | Closed | High |  | AI / RAG - KB | Defaulted to LLM mode: LlmRagRetriever reads ContentMd from SQL, keyword-prefilters, then queries the LLM (falls back to keyword ranking if the LLM errors) | 2026-07-17
OI-74 | No place to view system errors: exceptions only appeared in the console, and audit_logs was cluttered with technical records | Observability | Dev | NguyenTung309 | Closed | Medium |  | Admin / Logging | Serilog events at Warning level and above are now written to system_logs; added an admin tab with filtering + stack traces; aggregated HTTP 2xx/4xx/5xx counts by hour | 2026-07-19
OI-75 | Playwright artifacts (report, test-results, temp folders) were being committed to the repo | Repo hygiene | Dev | NguyenTung309 | Closed | Low |  | Repo / .gitignore | Added .gitignore entries for the Playwright report, test-results, and isolated temp folders | 2026-07-22
OI-76 | The LLM response had no usage block (a gateway-type provider) → every call recorded 0 tokens, 0 cost; the monthly cost cap stopped working from 2026-07-07; the UI showed cost = 0 | Bug | Dev | NguyenTung309 | Closed | Critical |  | AI / Cost ledger | Added LlmTokenEstimator to count tokens locally (Microsoft.ML.Tokenizers), tagged claude_cost_ledger with an IsEstimated flag (migration 0086), added a warning when unit pricing is missing, and formatted cost to 4 decimal places | 2026-07-25
OI-77 | Repeated FK__leads__contact_i__0C85DE4D errors (11k log lines): the adapter took contact_id directly from the LLM's plan, and RequiredGuid only validated GUID format, so fabricated IDs still reached SaveChanges | Bug | Runtime log / system_logs | NguyenTung309 | Closed | Critical |  | Agent / Lead pipeline | Added a contact-existence check in LeadAgentRunner.CreateWithSkillsAsync before running the skill; throws KeyNotFoundException → gRPC returns NotFound | 2026-07-25
OI-78 | AgentScheduleWorker shared a single scope/AppDbContext across a batch of 10 schedules → one failing lead caused 6 schedules to fail together, rolling back agent_traces and destroying the evidence | Bug | Runtime log | NguyenTung309 | Closed | High |  | Agent / Scheduler | Gave each schedule its own scope (matching ContentReviewDispatchWorker) | 2026-07-25
OI-79 | A sub-agent in the ReAct loop returned Success=true even when it only refused in text or its tool call failed → orchestration reported work as complete that had never actually run | Bug | Dev | NguyenTung309 | Closed | Critical |  | AI / Back-office agents | Split BackOfficeGuardrail out of BaseGuardrail; flagged unresolvedToolError; now reports refused_without_tool_use / unknown_tool errors. Verified: research-agent went from 0 → 3 tool_executed, 130/130 tests passing | 2026-07-26
OI-80 | Docker published SQL Server on 127.0.0.1:11433 (IPv4 only), but Windows resolved localhost to ::1 first → SYN packets were dropped and the connection hung until Connect Timeout. The symptom shown was 'Timeout expired... obtaining a connection from the pool' (identical to pool exhaustion). BackgroundServiceExceptionBehavior defaults to StopHost, so AgentService exited with code -532462766 before Kestrel could bind | Bug | Runtime log | NguyenTung309 | Closed | Critical |  | Config / SQL connection | Changed the connection string to 127.0.0.1 (IPv4 loopback). Measured with Connect Timeout=8: localhost failed after 8118ms, 127.0.0.1 connected in 135ms | 2026-08-01
OI-81 | When a customer sent several short messages in quick succession, the AI generated one reply per message, answering the greeting before reading the full question | Bug | Customer | thanglm240723 | Closed | Medium |  | AI auto-reply | Added AiReplyDebouncer: a sliding per-conversation timer (default 6s) that resets on every new message; AiAutoReplyResumer merges the whole block of unanswered messages into a single prompt | 2026-08-05
OI-82 | "Overview" (analytics) page: total conversation count displayed was double the real figure (8 instead of 4) | Bug | User | Thanglm240723 | Closed | High |  | DB (kpi_daily) / KpiAggregator / Analytics AP | aggregate() was summing the backend's platform="all" summary row together with the 3 real channel rows → switched to using the filtered visibleRows instead of the raw rows | 2026-06-08
OI-83 | The AI's reply leaked the [PHONE]/[EMAIL] placeholder instead of the real phone/email the customer had just provided, in the trial-registration confirmation message | Bug | User | Thanglm240723 | Closed | Medium |  | Agent-Chat / PII Redaction | Did not change the redaction code — instead updated the KB-04 script: the AI no longer repeats the phone/email, it just confirms briefly and hands off to a salesperson to process the registration, sidestepping the display bug | 2026-06-08
OI-84 | The /api/sale-assist/upsell-suggestions endpoint looped over up to 20 hot leads, sequentially calling RAG + the Claude LLM 20 times to generate upsell suggestions for each lead, without caching or saving to the DB. The frontend triggered this query automatically (staleTime 60s), burning a large amount of LLM tokens, causing heavy request latency, and lagging the UI every time the conversations page was revisited | Bug | DEV | Thanglm240723 | Closed | High |  | Sale Assist / LLM Upsell / API | Upsell suggestions are now saved to DB/Redis after successful generation; regeneration only triggers via a Background Job when a lead has new activity (LastActivityAt changes). The API endpoint now only reads from the DB cache to return an instant response (<50ms).

## 9. Change Log
Requirements Change Log
Add a row for every change after the first approved baseline. Include the specific section affected, the reason, and who approved the change.
Change ID | Date | Version | Change Type | Change Description | Section / Feature Affected | Reason / Justification | Impact Assessment | Changed by | Approved by | Approval Date
CHG-001 | 2026-06-01 | v0.1.0 | Initial baseline | Project kickoff and requirements baseline established | All sections | Project inception and stakeholder alignment | N/A - Initial document creation | thanglm240723 | NguyenTung309 | 2026-06-01
CHG-002 | 2026-06-05 | v0.2.0 | Feature Addition | Added JWT authentication with refresh token rotation | Login & Authentication | Security requirement: prevent token replay attacks | High - Core authentication mechanism, affects all authenticated endpoints | NguyenTung309 | NguyenTung309 | 2026-06-05
CHG-003 | 2026-06-10 | v0.3.0 | Feature Addition | Implemented multi-tenant architecture with tenant isolation | Infrastructure, Database Schema | Enable SaaS model with complete data isolation per customer | High - All domain entities require TenantId, query filters applied globally | thanglm240723 | NguyenTung309 | 2026-06-10
CHG-004 | 2026-06-15 | v0.4.0 | Feature Addition | Omnichannel inbox with Facebook Messenger and Pancake integration | Omnichannel Inbox | Customer requirement: unified inbox for all social channels | High - New module with webhook consumers and polling services | thanglm240723 | NguyenTung309 | 2026-06-15
CHG-005 | 2026-06-20 | v0.5.0 | Feature Addition | Knowledge Base with vector search via Qdrant | Knowledge Base | Enable semantic search for customer support agents and AI assistants | Medium - New vector store dependency, embedding model configuration required | NguyenTung309 | NguyenTung309 | 2026-06-20
CHG-006 | 2026-06-25 | v0.6.0 | Feature Addition | AI chat agent with ReAct pattern and tool orchestration | Agent Orchestration | Core AI capability: autonomous agents with tool access | High - New gRPC service, LLM provider integration, tool registry | thanglm240723 | NguyenTung309 | 2026-06-25
CHG-007 | 2026-06-28 | v0.7.0 | Feature Addition | Auto-reply system with conversation context and guardrails | Chat Scenarios | Reduce manual response time by 80% through AI-powered replies | High - Requires content review gate and fail-closed safety mechanisms | thanglm240723 | NguyenTung309 | 2026-06-28
CHG-008 | 2026-07-01 | v0.8.0 | Enhancement | RBAC permission system with role-based endpoint protection | Permission Matrix | Compliance requirement: granular access control per user role | Medium - All endpoints require permission declaration, seed data required | NguyenTung309 | NguyenTung309 | 2026-07-01
CHG-009 | 2026-07-05 | v0.9.0 | Feature Addition | Cost tracking and monthly cap enforcement for LLM usage | Agent Orchestration, Business Rules | Budget control: prevent runaway AI costs exceeding monthly limit | Medium - Preflight check, mid-run reservation, ledger write even at cost=0 | thanglm240723 | NguyenTung309 | 2026-07-05
CHG-010 | 2026-07-08 | v1.0.0 | Milestone | MVP release: core features complete and production-ready | All modules | First production deployment for pilot customers | High - Full system goes live, monitoring and support required | NguyenTung309 | NguyenTung309 | 2026-07-08
CHG-011 | 2026-07-10 | v1.1.0 | Feature Addition | Content review gate with multi-tier escalation | Content Pipeline | Brand safety: prevent off-brand or risky content from publishing | Medium - New workflow step, tiered chat routing for review requests | thanglm240723 | NguyenTung309 | 2026-07-10
CHG-012 | 2026-07-13 | v1.2.0 | Feature Addition | Background jobs system with notification feed | Agent Orchestration, Notifications | User experience: track long-running tasks and receive completion alerts | High - New job runner, notification queue, UI feed component | NguyenTung309 | NguyenTung309 | 2026-07-13
CHG-013 | 2026-07-20 | v1.3.0 | Feature Addition | Lead management with scoring engine and lifecycle stages | Lead Management | Sales enablement: prioritize high-intent leads and track conversion funnel | High - New module with 8 default scoring rules, 5 lifecycle stages | thanglm240723 | NguyenTung309 | 2026-07-20
CHG-014 | 2026-07-25 | v1.4.0 | Enhancement | Content prompt chaining with 6-phase refinement pipeline | Content Pipeline | Quality improvement: iterative refinement produces better content | Medium - Extended pipeline (P1-P6), backward compatible with single-phase | thanglm240723 | NguyenTung309 | 2026-07-25
CHG-015 | 2026-07-26 | v1.4.1 | Bug Fix | Fixed agent refusal false-positive detection using unresolvedToolError | Agent Orchestration | Reliability: prevent false green status when agent refuses tasks | Low - Internal trace validation improvement, no API changes | NguyenTung309 | NguyenTung309 | 2026-07-26
CHG-016 | 2026-08-05 | v1.5.0 | Enhancement | Orchestrator intervention: pause, resume, and manual task output | Agent Orchestration | Control: allow human oversight in complex multi-step workflows | Medium - New control endpoints, plan approval workflow | thanglm240723 | NguyenTung309 | 2026-08-05
CHG-017 | 2026-08-09 | v1.5.1 | Removal | Removed Ads and Payment/Revenue modules from codebase | Ads Module, Payment Module | Scope reduction: out-of-scope for MVP, deferred to Phase 2 | Low - Code removed, database schema preserved for future migration | NguyenTung309 | NguyenTung309 | 2026-08-09
CHG-018 | 2026-08-09 | v1.5.2 | Bug Fix | Fixed SQL migration replay logic in run-all.bat via ledger tracking | Infrastructure, Database Schema | Deployment reliability: ensure migrations apply correctly on existing databases | Low - Internal tooling improvement, no production impact | thanglm240723 | NguyenTung309 | 2026-08-09
CHG-019 | 2026-08-11 | v1.6.0 | Documentation | Completed comprehensive test suite: Unit (5.1), Integration (5.2), System (5.3) | Quality Assurance | Production readiness: achieve 90%+ source code coverage | High - 14 unit test methods (172 cases), 6 integration sheets (65 cases), 5 system workflows | thanglm240723 | NguyenTung309 | 2026-08-11
CHG-020 | 2026-08-12 | v1.6.1 | Documentation | Updated RTW Change Log with comprehensive project history | Requirements Change Log | Traceability: document all requirement changes from inception to current state | Low - Documentation update, no functional changes | thanglm240723 | NguyenTung309 | 2026-08-12